## Phase 3 Summary
Public Service Semester for University Students in Bangladesh - Phase 3 Research Summary
Feasibility, capacity, financial, legal and governance research - compiled 2026-10-15 - built on the Phase 1 national database (173 universities; 148 government organizations)
THE RESEARCH QUESTION
Model under evaluation | Supervised public service semester within university degrees; students placed in government institutions matched to their disciplines | Planning hypothesis to TEST: 300,000 participants/year | Protocol
This phase does NOT produce | No government presentation, no formal policy proposal - research, evaluation and program design only | Next phase prepares the presentation and proposal | Protocol
PIPELINE FINDINGS (Dataset 12)
Total tertiary enrollment baseline (2020) | 4690876 | public system 4,362,187 + private 328,689 | SRC-05; ASM-01
Annual graduates, all sectors (2021) | 344528 | only verified national graduate figure | SRC-06
Estimated final-year cohort (uniform-4-year assumption) | 1172719 | derivation; NU year-of-study decomposition missing (GAP-19) | ASM-03
Direct university final-year pool (public direct + private) | 130178 | mixed vintage 2015/2021 - order of magnitude | ASM-03/04
KEY FINDING: 300,000/year exceeds the direct-university pool by | 169822 | NU college participation is structurally REQUIRED for the 300k target | PL-15
300,000 as share of national final-year cohort | 25.6% | about 1 in 4 final-year students nationwide | ASM-03
HOST CAPACITY AND SCENARIOS (Datasets 13, 15, 16)
Verified host network (largest nodes) | 65,567 primary schools; 19,211-21,086 secondary; 2,260-2,500 NU colleges; 418 upazila health complexes; 495 upazilas; 4,554-4,585 unions; 330 pourashavas; 12 city corporations | institution COUNTS are verified; hosting DENSITY per institution is an assumption (GAP-21) | SRC-81 to SRC-91
Theoretical annual placement capacity (medium) | 322174 | NOT operational capacity - supervisors and coordination are the binding constraints | ASM-11 to ASM-16
Trained supervisors needed at 1:20 (300k scenario) | 15000 | about 1% of all filled government posts (1,464,350) | ASM-07
Government vacancies (June 2025) | 521922 | vacancies are NOT hosting capacity - analytical distinction documented | SRC-09
FINANCIAL MODEL (Dataset 17) - PRELIMINARY ESTIMATES
Per-participant cost (at 300k scale) | BDT 25,250 - 69,900 | stipend BDT 3,000-8,000/month x 4 months anchored to DYD allowance 4,500 / internships 10-15k / minimum wage 12,500 | ASM-21
Total annual cost, 100,000 participants | BDT ~2.9 - 8.2 billion (290-820 crore) | low - high scenarios | Dataset 17
Total annual cost, 300,000 participants | BDT ~8.4 - 23.3 billion (840 - 2,330 crore) | low - high scenarios | Dataset 17
Corruption-reduction savings counted as benefit? | NO - excluded per research protocol | no guaranteed savings claimed anywhere in the model | ASM-22
LEGAL FEASIBILITY (Dataset 18)
National Service Ordinance 1970 status | DORMANT at best (never commenced; possibly repealed); MILITARY scope; male-only | verified from official bdlaws full text - provides NO usable authority; new legislation required for a compulsory element | SRC-46 to SRC-48
UGC enforcement lever | Grant withholding (UGC Order 1973, s.5(3)) - financial, not curricular | curriculum authority sits with university senates/academic councils | SRC-49
Domestic precedent | National Service Programme (since 2009-10, Ministry of Youth and Sports): training + 2-year government office placements | administrative pilot possible WITHOUT new primary legislation | SRC-55/56
Compulsory degree requirement needs | New primary legislation + equality-compliant (gender-neutral) design | pilots can run voluntary/credit-elective under existing university autonomy | LEG-15
INTERNATIONAL EVIDENCE (Dataset 19)
Closest structural model | Indonesia KKN - mandatory, credit-bearing, community-embedded since 1973 (50+ years) | UGM alone: 6,000-7,000 students/year in 400+ villages | SRC-57 to SRC-59
Scale proof | Nigeria NYSC: from 2,364 (1973-74) to ~400,000 corps members/year | proves 300k-scale mobilization is administratively possible in a comparable country | SRC-63/64
Central warning | NYSC became a corruption object itself (certificate fraud - 2018 ministerial resignation; ICPC convictions) | anti-fraud design (digital verification, biometrics, audits) required from day one | SRC-65
Voluntary alternative evidence | India NSS: ~3.65M volunteers, 771+ universities - voluntary campus-unit model | relevant if Bangladesh tests voluntary uptake first | SRC-66/67
ANTI-CORRUPTION EVIDENCE BASE (Dataset 20)
Uganda newspaper campaign (Reinikka & Svensson 2005, QJE) | Grant capture fell from ~80% to under 20% when citizens could monitor school grants | strongest causal evidence that information + monitoring reduces capture | SRC-73/74
Brazil audit disclosures (Ferraz & Finan 2008, QJE) | Publicized randomized audits reduced corrupt mayors' reelection chances | disclosure + consequences = accountability | SRC-75
Indonesia audit experiment (Olken 2007, JPE) | Top-down official audits cut missing expenditures ~8pp; grassroots monitoring effects were weaker | who monitors and what follows detection MATTERS - program must pair students with real verification and consequences | SRC-76
India social audits (MGNREGA) | Regular audits reduced wage leakage, but corruption ADAPTED and relocated | monitoring is not one-time; anatomy of corruption changes | SRC-77
Honest bottom line | No international program has been shown by rigorous evidence to reduce corruption through student service | the mechanisms are plausible and evidence-adjacent - Bangladesh would be testing a hypothesis, not importing a proven model | Report s.7
PHASED PATH (Dataset 23)
Recommended pathway | PH-0 design (12 mo) > PH-1 voluntary pilot 5-10k (2 yrs) > PH-2 50k > PH-3 100-200k > PH-4 300k conditional | every expansion gated by independent evaluation with pre-registered criteria | Dataset 23
Standing rule | Scale never expands faster than the supervisor pipeline | supervision, not buildings, is the binding constraint | RSK-09
RESEARCH INTEGRITY
New sources verified this phase | 54 | SRC-46 to SRC-99; combined with Phase 1: 99 sources | Dataset 25
New data gaps registered | 12 | GAP-18 to GAP-29; program total 29 gaps with RTI pathways | Dataset 26
Assumptions documented | 22 | every derived number traceable to ASM-xx | Dataset 24

## D12 Pipeline
Dataset 12: Education-to-Service Pipeline (verified inputs + derived cohorts)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
stage_id | pipeline_stage | value | unit | data_type | source_or_assumption | notes
PL-01 | Total university-system enrollment (public universities incl. National University and Bangladesh Open University affiliated colleges) | 4362187 | students | Actual count (UGC annual report 2020, as reported) | SRC-05 | Reported for 46 public universities including NU + BOU affiliated college enrollment, 2020
PL-02 | Total private university enrollment (2020) | 328689 | students | Actual count (UGC annual report 2020) | SRC-05 | 107 private universities
PL-03 | Total tertiary enrollment baseline (2020, all sectors) | 4690876 | students | Derived calculation (PL-01 + PL-02) | ASM-01 | Baseline used for pipeline modeling; 2020 is the most recent year with a verified all-sector total
PL-04 | National University affiliated institutions (2025 reporting) | 2500 | institutions | Reported figure (TBS interview) | SRC-90 | NU "oversees around 2,500 educational institutions... providing higher education to 4 million students" (May 2025)
PL-05 | National University enrollment (2025 reporting) | 4000000 | students | Reported figure (TBS interview) | SRC-90 | Approximate; scope includes pass, honours and professional courses; consistent in magnitude with PL-01 system total but vintage differs (2020 vs 2025) - treat as range, flag inconsistency
PL-06 | Annual university graduates, all sectors (2021) | 344528 | students/year | Actual count (UGC annual report via Bonik Barta) | SRC-06 | Only verified national graduate figure; sector split not published
PL-07 | Graduates as share of total enrollment | 7.3 | percent | Derived calculation (PL-06 / PL-03) | ASM-02 | Illustrates graduation rate vs stock; different reporting years (2021 graduates vs 2020 enrollment) - indicative only
PL-08 | Average annual intake proxy (uniform-cohort assumption) | 1172719 | students/year | Derived calculation (PL-03 / 4) | ASM-03 | Assumes uniform distribution across 4 years of a 4-year honours degree; ignores 2-3 year pass courses, masters students, attrition and session delay
PL-09 | Estimated final-year cohort (service-semester eligible under a final-year model) | 1172719 | students/year | Derived calculation | ASM-03 | Same assumption as PL-08; if mean program length is 4.5 years the figure falls to about 1,042,000; if NU pass courses dominate, it falls further
PL-10 | Final-year cohort in direct-teaching public universities only (2015 basis) | 52651 | students/year | Derived calculation ((PL-12 - BOU 243,928)/4) | ASM-03; ASM-04 | Direct public universities excluding BOU distance students
PL-11 | Final-year cohort in private universities (2021 basis) | 77527 | students/year | Derived calculation (PL-13 / 4) | ASM-03 | 310,107 enrolled / 4
PL-12 | Public university direct enrollment incl. BOU (2015) | 454530 | students | Actual count (BANBEIS via 2016 analysis) | SRC-03 | 33 public universities; includes Bangladesh Open University (243,928)
PL-13 | Private university enrollment (2021) | 310107 | students | Actual count (UGC) | SRC-04 | All UGC-listed private universities
PL-14 | Direct university final-year pool (public direct + private) | 130178 | students/year | Derived calculation (PL-10 + PL-11) | ASM-03; ASM-04 | Mixed data vintage (2015 public direct / 2021 private); order-of-magnitude estimate
PL-15 | KEY FINDING - 300,000 annual participants exceed the direct-university final-year pool by 169,822 | 169822 | students (shortfall = 300,000 - PL-14) | Derived calculation | ASM-03 | A 300,000/year program cannot be filled from public (direct) + private university final-year students alone; participation of National University affiliated college students is structurally REQUIRED
PL-16 | 300,000 as share of national final-year cohort (incl. NU colleges) | 25.6 | percent | Derived calculation (300,000 / PL-09) | ASM-03 | Roughly one in four final-year students nationwide
PL-17 | 300,000 as share of total enrollment | 6.4 | percent | Derived calculation (300,000 / PL-03) | ASM-01 | About 1 in 16 of all enrolled students each year
PL-18 | 100,000 as share of national final-year cohort | 8.5 | percent | Derived calculation (100,000 / PL-09) | ASM-03 | A 100,000/year program can be run within direct universities + partial NU college participation
PL-19 | Annual first-year enrollment in 50 public universities (2023) | 49883 | students | Actual count (BANBEIS via Daily Sun) | SRC-07 | Out of 1.05 million eligible candidates; first-year seats offered 50,455
PL-20 | Data required to distinguish eligible/enrolled/placed/completing students | NA | dataset | NOT PUBLICLY AVAILABLE | GAP-18; GAP-19 | Requires: enrollment by year-of-study per institution; placement registry; completion records - see missing-data register

## D13 Scenarios
Dataset 13: Participation Scenarios (100,000 / 200,000 / 300,000 per year)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
scenario | metric | value | unit | data_type | basis | notes
S1 - Conservative | Annual participants | 100000 | students | Planning scenario | User-specified target hypothesis; not a verified capacity figure
S1 - Conservative | Concurrent placements (two intakes/year) | 50000 | students | Derived (ASM-05) | 100000 / 2 | Assumes semester system with two placement windows per calendar year
S1 - Conservative | Host institutions needed at 10 students per institution | 10000 | institutions | Derived (ASM-06) | 100000 / 10 | Plausible average hosting density for upazila-level offices
S1 - Conservative | Host institutions needed at 20 students per institution | 5000 | institutions | Derived (ASM-06) | 100000 / 20 | Higher-density model requiring dedicated coordination rooms
S1 - Conservative | Trained supervisors at 1:10 ratio | 10000 | supervisors | Derived (ASM-07) | 100000 / 10 | High-touch ratio suitable for health, procurement-adjacent and data-sensitive assignments
S1 - Conservative | Trained supervisors at 1:20 ratio (recommended planning default) | 5000 | supervisors | Derived (ASM-07) | 100000 / 20 | Balanced ratio for general administrative support placements
S1 - Conservative | Trained supervisors at 1:30 ratio | 3333 | supervisors | Derived (ASM-07) | 100000 / 30 | Stretch ratio only for low-risk, batch-style digitization or survey support tasks
S1 - Conservative | Students per upazila if spread across all 495 upazilas | 202 | students/upazila/year | Derived (ASM-08) | 100000 / 495 | 495 upazilas verified (SRC-81); actual allocation would follow enrollment distribution (GAP-18)
S1 - Conservative | Students per district if spread across all 64 districts | 1562.5 | students/district/year | Derived (ASM-08) | 100000 / 64
S1 - Conservative | Sector placement - Education (schools, colleges, education offices) | 30000 | students/year | Planning assumption (ASM-09) | 30% of 100000 | Largest verified host network: 65,567 primary schools (SRC-87), 19,211-21,086 secondary institutions (SRC-88; SRC-89), 2,260-2,500 NU colleges (SRC-91; SRC-90)
S1 - Conservative | Sector placement - Health | 15000 | students/year | Planning assumption (ASM-09) | 15% of 100000 | 418 upazila health complexes (SRC-85), district hospitals; BMDC internship precedent (SRC-94)
S1 - Conservative | Sector placement - Local government and rural development | 15000 | students/year | Planning assumption (ASM-09) | 15% of 100000 | 4,554-4,585 union parishads (SRC-81; SRC-82), 330 pourashavas (SRC-83), 12 city corporations (SRC-84), 495 upazila parishads (SRC-81)
S1 - Conservative | Sector placement - Public administration and records management | 10000 | students/year | Planning assumption (ASM-09) | 10% of 100000 | 64 district administrations, upazila offices, land offices
S1 - Conservative | Sector placement - Digital government and ICT | 8000 | students/year | Planning assumption (ASM-09) | 8% of 100000 | ICT Division, a2i, union digital centers (count requires verification - GAP-20)
S1 - Conservative | Sector placement - Research, statistics and data quality | 6000 | students/year | Planning assumption (ASM-09) | 6% of 100000 | BBS district offices, BANBEIS
S1 - Conservative | Sector placement - Agriculture and fisheries | 5000 | students/year | Planning assumption (ASM-09) | 5% of 100000 | Upazila agriculture extension offices under Ministry of Agriculture
S1 - Conservative | Sector placement - Social protection and social welfare | 5000 | students/year | Planning assumption (ASM-09) | 5% of 100000 | 64 district + upazila social welfare offices
S1 - Conservative | Sector placement - Environment and climate | 3000 | students/year | Planning assumption (ASM-09) | 3% of 100000 | Department of Environment offices
S1 - Conservative | Sector placement - Public procurement monitoring (observer role only) | 3000 | students/year | Planning assumption (ASM-09) | 3% of 100000 | CPTU and procuring entities - documentation organization only, no evaluation role
S2 - Intermediate | Annual participants | 200000 | students | Planning scenario | User-specified target hypothesis; not a verified capacity figure
S2 - Intermediate | Concurrent placements (two intakes/year) | 100000 | students | Derived (ASM-05) | 200000 / 2 | Assumes semester system with two placement windows per calendar year
S2 - Intermediate | Host institutions needed at 10 students per institution | 20000 | institutions | Derived (ASM-06) | 200000 / 10 | Plausible average hosting density for upazila-level offices
S2 - Intermediate | Host institutions needed at 20 students per institution | 10000 | institutions | Derived (ASM-06) | 200000 / 20 | Higher-density model requiring dedicated coordination rooms
S2 - Intermediate | Trained supervisors at 1:10 ratio | 20000 | supervisors | Derived (ASM-07) | 200000 / 10 | High-touch ratio suitable for health, procurement-adjacent and data-sensitive assignments
S2 - Intermediate | Trained supervisors at 1:20 ratio (recommended planning default) | 10000 | supervisors | Derived (ASM-07) | 200000 / 20 | Balanced ratio for general administrative support placements
S2 - Intermediate | Trained supervisors at 1:30 ratio | 6667 | supervisors | Derived (ASM-07) | 200000 / 30 | Stretch ratio only for low-risk, batch-style digitization or survey support tasks
S2 - Intermediate | Students per upazila if spread across all 495 upazilas | 404 | students/upazila/year | Derived (ASM-08) | 200000 / 495 | 495 upazilas verified (SRC-81); actual allocation would follow enrollment distribution (GAP-18)
S2 - Intermediate | Students per district if spread across all 64 districts | 3125 | students/district/year | Derived (ASM-08) | 200000 / 64
S2 - Intermediate | Sector placement - Education (schools, colleges, education offices) | 60000 | students/year | Planning assumption (ASM-09) | 30% of 200000 | Largest verified host network: 65,567 primary schools (SRC-87), 19,211-21,086 secondary institutions (SRC-88; SRC-89), 2,260-2,500 NU colleges (SRC-91; SRC-90)
S2 - Intermediate | Sector placement - Health | 30000 | students/year | Planning assumption (ASM-09) | 15% of 200000 | 418 upazila health complexes (SRC-85), district hospitals; BMDC internship precedent (SRC-94)
S2 - Intermediate | Sector placement - Local government and rural development | 30000 | students/year | Planning assumption (ASM-09) | 15% of 200000 | 4,554-4,585 union parishads (SRC-81; SRC-82), 330 pourashavas (SRC-83), 12 city corporations (SRC-84), 495 upazila parishads (SRC-81)
S2 - Intermediate | Sector placement - Public administration and records management | 20000 | students/year | Planning assumption (ASM-09) | 10% of 200000 | 64 district administrations, upazila offices, land offices
S2 - Intermediate | Sector placement - Digital government and ICT | 16000 | students/year | Planning assumption (ASM-09) | 8% of 200000 | ICT Division, a2i, union digital centers (count requires verification - GAP-20)
S2 - Intermediate | Sector placement - Research, statistics and data quality | 12000 | students/year | Planning assumption (ASM-09) | 6% of 200000 | BBS district offices, BANBEIS
S2 - Intermediate | Sector placement - Agriculture and fisheries | 10000 | students/year | Planning assumption (ASM-09) | 5% of 200000 | Upazila agriculture extension offices under Ministry of Agriculture
S2 - Intermediate | Sector placement - Social protection and social welfare | 10000 | students/year | Planning assumption (ASM-09) | 5% of 200000 | 64 district + upazila social welfare offices
S2 - Intermediate | Sector placement - Environment and climate | 6000 | students/year | Planning assumption (ASM-09) | 3% of 200000 | Department of Environment offices
S2 - Intermediate | Sector placement - Public procurement monitoring (observer role only) | 6000 | students/year | Planning assumption (ASM-09) | 3% of 200000 | CPTU and procuring entities - documentation organization only, no evaluation role
S3 - Target hypothesis | Annual participants | 300000 | students | Planning scenario | User-specified target hypothesis; not a verified capacity figure
S3 - Target hypothesis | Concurrent placements (two intakes/year) | 150000 | students | Derived (ASM-05) | 300000 / 2 | Assumes semester system with two placement windows per calendar year
S3 - Target hypothesis | Host institutions needed at 10 students per institution | 30000 | institutions | Derived (ASM-06) | 300000 / 10 | Plausible average hosting density for upazila-level offices
S3 - Target hypothesis | Host institutions needed at 20 students per institution | 15000 | institutions | Derived (ASM-06) | 300000 / 20 | Higher-density model requiring dedicated coordination rooms
S3 - Target hypothesis | Trained supervisors at 1:10 ratio | 30000 | supervisors | Derived (ASM-07) | 300000 / 10 | High-touch ratio suitable for health, procurement-adjacent and data-sensitive assignments
S3 - Target hypothesis | Trained supervisors at 1:20 ratio (recommended planning default) | 15000 | supervisors | Derived (ASM-07) | 300000 / 20 | Balanced ratio for general administrative support placements
S3 - Target hypothesis | Trained supervisors at 1:30 ratio | 10000 | supervisors | Derived (ASM-07) | 300000 / 30 | Stretch ratio only for low-risk, batch-style digitization or survey support tasks
S3 - Target hypothesis | Students per upazila if spread across all 495 upazilas | 606.1 | students/upazila/year | Derived (ASM-08) | 300000 / 495 | 495 upazilas verified (SRC-81); actual allocation would follow enrollment distribution (GAP-18)
S3 - Target hypothesis | Students per district if spread across all 64 districts | 4687.5 | students/district/year | Derived (ASM-08) | 300000 / 64
S3 - Target hypothesis | Sector placement - Education (schools, colleges, education offices) | 90000 | students/year | Planning assumption (ASM-09) | 30% of 300000 | Largest verified host network: 65,567 primary schools (SRC-87), 19,211-21,086 secondary institutions (SRC-88; SRC-89), 2,260-2,500 NU colleges (SRC-91; SRC-90)
S3 - Target hypothesis | Sector placement - Health | 45000 | students/year | Planning assumption (ASM-09) | 15% of 300000 | 418 upazila health complexes (SRC-85), district hospitals; BMDC internship precedent (SRC-94)
S3 - Target hypothesis | Sector placement - Local government and rural development | 45000 | students/year | Planning assumption (ASM-09) | 15% of 300000 | 4,554-4,585 union parishads (SRC-81; SRC-82), 330 pourashavas (SRC-83), 12 city corporations (SRC-84), 495 upazila parishads (SRC-81)
S3 - Target hypothesis | Sector placement - Public administration and records management | 30000 | students/year | Planning assumption (ASM-09) | 10% of 300000 | 64 district administrations, upazila offices, land offices
S3 - Target hypothesis | Sector placement - Digital government and ICT | 24000 | students/year | Planning assumption (ASM-09) | 8% of 300000 | ICT Division, a2i, union digital centers (count requires verification - GAP-20)
S3 - Target hypothesis | Sector placement - Research, statistics and data quality | 18000 | students/year | Planning assumption (ASM-09) | 6% of 300000 | BBS district offices, BANBEIS
S3 - Target hypothesis | Sector placement - Agriculture and fisheries | 15000 | students/year | Planning assumption (ASM-09) | 5% of 300000 | Upazila agriculture extension offices under Ministry of Agriculture
S3 - Target hypothesis | Sector placement - Social protection and social welfare | 15000 | students/year | Planning assumption (ASM-09) | 5% of 300000 | 64 district + upazila social welfare offices
S3 - Target hypothesis | Sector placement - Environment and climate | 9000 | students/year | Planning assumption (ASM-09) | 3% of 300000 | Department of Environment offices
S3 - Target hypothesis | Sector placement - Public procurement monitoring (observer role only) | 9000 | students/year | Planning assumption (ASM-09) | 3% of 300000 | CPTU and procuring entities - documentation organization only, no evaluation role

## D14 Program Mapping
Dataset 14: Discipline-to-Service Assignment Mapping (27 discipline clusters)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
discipline_cluster | example_verified_programs | primary_host_sector | sample_assignments | permitted_role_limits | special_arrangements
Computer Science and Engineering | CSE at DU (PROG-0030), BUET (SRC-40), CUET (SRC-36), BRAC U CSE, NSU CSE | Digital government and ICT | Records digitization on approved project lists; portal content organization; data-entry quality assurance; application testing on public systems | No access to personal or classified records; no independent database administration; all work on government-approved project instances | Place in batches with technical mentor; equipment: workstations provided by host
Electrical and Electronic Engineering | EEE at DU (PROG-0039), BUET, CUET | Public infrastructure monitoring | Streetlight and meter inventories (visual, public-space); energy-audit data collection in government buildings | No electrical safety-critical work; observation and inventory only | Safety induction mandatory
Civil Engineering | BUET Civil (SRC-37), CUET Civil | Public infrastructure monitoring | Citizen-side condition checklists for school and union buildings; footbridge and drainage inventory mapping | No structural assessment sign-off; data feeds to qualified engineers only | Works under LGED/PWD supervision
Medicine and Public Health | DU Faculty of Medicine (PROG-0012); MBBS colleges | Health | Community clinic logistics support; immunization campaign recording; health-education sessions; follow-up of defaulters | MBBS graduates already complete a compulsory 1-year rotatory internship (SRC-94) - the service semester for medical students must be aligned to, not duplicate, that internship | Placement in UHCs and community clinics; BMDC alignment required
Pharmacy | DU Faculty of Pharmacy (PROG-0007) | Health | Public awareness on rational drug use; retail price-display verification visits (accompanied) | No inspection powers; accompanied observation only | Pairs with DGDA awareness campaigns
Nursing and Midwifery | Nursing colleges (under health sector) | Health | Clinic queue management support; maternal-health education sessions | Clinical tasks only under licensed supervision | Requires professional council alignment
Law | DU Faculty of Law (PROG-0003) | Public information; justice-adjacent support | Supervised legal research for law reform commissions; legal-aid clinic reception and form assistance; RTI awareness sessions for citizens | No legal advice without supervision; no representation; no case-file access beyond authorized clinic materials | Supervising lawyer mandatory; university law faculty agreement
Statistics | RU/BUET statistics programs; DU Applied Mathematics adjacent | Research, statistics and data quality | Survey enumeration support on BBS-authorized surveys; aggregate data-quality checks; tabulation for district statistics offices | Works only on authorized survey instruments; household data handled per BBS confidentiality rules | BBS district office placements
Economics | DU Economics (PROG-0037), RU Economics | Public administration; planning | Secondary-data compilation for district plans; market price bulletin compilation support | Analysis of published data only | Planning office placements
Business, Accounting and Finance | DU Business Studies (PROG-0004), NSU business programs | Public procurement monitoring; records management | Bid document organization (non-evaluation); asset register digitization; office records scheduling | NO role in bid evaluation, opening or procurement decisions - documentation organization only | CPTU-endorsed standard operating procedure required
Environmental Science | DU Earth and Environmental Sciences (PROG-0008) | Environment and climate | Water-sample collection support; tree census; air-quality station assistance | Sampling under DoE protocols; no enforcement role | DoE division office placements
Agriculture | Agricultural universities (BAU system) | Agriculture | Farmer field-day support; crop-cut survey assistance; extension material distribution | Fieldwork under DAE officers | Upazila agriculture office placements
Veterinary and Livestock | Veterinary colleges | Agriculture | Vaccination campaign logistics; poultry farm registry updates (accompanied) | No clinical sign-off | Upazila livestock office placements
Fisheries | Marine/fisheries faculties | Agriculture | Pond census support; hatchery record digitization | Accompanied fieldwork | Upazila fisheries office placements
Education and B.Ed | Education faculties and NU education colleges | Education | After-school tutoring support; school attendance register digitization; library organization | No independent teaching responsibility; supporting role under head teacher | School placements with head-teacher supervision
Bangla, English and Humanities | DU Bangla (PROG-0020), RU English (SRC-43) | Public information | Citizen charter simplification; form translation; public notice drafting; archive documentation | Draft products reviewed by controlling officer before publication | District information office placements
Social Work and Sociology | DU Sociology, Anthropology (PROG-0015) | Social protection | Accompanied beneficiary-home verification fieldwork; old-age home activity support; help-desk assistance | Verification visits ALWAYS accompanied by a government officer; no benefit decisions | Social welfare office placements
Development Studies | DU Development Studies (PROG-0034) | Service delivery monitoring | Service-delivery observation surveys against published citizen charters; report drafting | Observation instruments pre-approved; findings go to program M&E unit, not directly public | Cabinet Division GRS-aligned placement
Journalism and Media | Media and journalism departments | Public information | Citizen information desks; RTI application help; community bulletin production | No investigative reporting using placement access; program neutrality rules apply | Information ministry field offices
Geography and GIS | Geography departments | Local government | Facility mapping (schools, clinics, water points); flood-exposure map drafts | Maps are decision-support inputs, not official records | LGD/a2i-aligned projects
Psychology and Counseling | DU Clinical Psychology (PROG-0028) | Social protection | Helpline support (trained and scripted); counseling-adjacent support services | No independent counseling practice; scripted helpline roles only | Helpline placements require vetting
History and Islamic/Asian Studies | DU History, Arabic (PROG-0018) | Records management | Archive box-listing; oral-history documentation of liberation war records | Archive handling per National Archives rules | National Archives and district record rooms
Physics, Chemistry and Basic Sciences | DU Science faculty programs | Education | School science-fair support; laboratory inventory in government schools | No hazardous-material handling | School placements
Architecture and Fine Arts | DU Fine Art (PROG-0010), Architecture programs | Local government; heritage | Public-space accessibility audit drafts; heritage building documentation; civic murals on request | Drafts reviewed by municipal engineers | City corporation and pourashava placements
Textile Engineering | Textile universities and colleges (SRC-95 sector) | Public administration (textile ministry programs) | Vocational training support in textile training institutes | No production-line responsibility | Ministry of Textiles and Jute institutions
Engineering (general industrial attachment precedent) | BUET engineering programs; polytechnic industrial attachment precedent (SRC-95) | Cross-sector | Existing 1-3 month industrial attachment formats can be re-hosted in government establishments where curriculum-compatible | If a program already requires industrial attachment, the service semester should SUBSTITUTE not add | University academic council approval per program
General NU college disciplines (BA/BSS/BBS/BSc pass and honours) | National University 2,260-2,500 affiliated colleges (SRC-91; SRC-90) | Education; local government; social protection | College-campus-based service assignments (library digitization, admission-camp support); union parishad record support near home college | Largest single participant pool - any 100,000+ program depends on this group; assignments must be feasible near the home college (ASM-10) | NU academic council and college governing bodies must approve credit recognition

## D15 Sector Mapping
Dataset 15: Government Sector and Host-Institution Mapping (14 sectors)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
sector | host_institutions_with_verified_counts | source_ids | relevant_disciplines | suitable_student_assignments | required_training | expected_service_duration | available_host_capacity | equipment_needs | data_access_and_confidentiality | key_risks | measurable_outputs
Public administration | Deputy Commissioner offices (64 districts); Upazila Nirbahi Officer complexes (495); Union Parishads (4,554-4,585) | SRC-81; SRC-82 | All general disciplines | Office records organization; citizen help desks; form-filling assistance; register digitization | 1-day orientation + host-office induction | 16 weeks (a semester) | High (one office per administrative unit) | Basic office space; desks | Public records handled under supervising officer custody; no personal files | Data confidentiality breach; workload displacement of staff | Registers digitized; help-desk logs; citizen assistance counts
Education | Government primary schools (65,567); secondary institutions (19,211-21,086); NU colleges (2,260-2,500) | SRC-87; SRC-88; SRC-89; SRC-91; SRC-90 | Education, languages, basic sciences, psychology | After-school tutoring; attendance register digitization; library organization; science-fair support | University orientation + head-teacher briefing | 16 weeks | Very high (largest host network) | Classroom/library space after hours | Student personal data must remain with school custody | Child-safeguarding failures (requires vetting + always-adult-present rule) | Tutoring hours; registers digitized; library catalogues
Healthcare | Upazila health complexes (418); district hospitals (64 districts); community clinics | SRC-85; SRC-86 | Medicine, public health, nursing, pharmacy | Queue management; campaign recording; health education; clinic logistics | Health-sector induction + professional-council alignment | Aligned to professional internship rules | High but regulated by professional councils | Clinic meeting rooms | Patient records strictly off-limits except authorized campaign registers | Patient-privacy breaches; clinical role creep | Campaign coverage records; queue statistics; education session counts
Agriculture | Upazila agriculture, fisheries and livestock offices; DAE district offices | Phase 1 org register BD-GOVT-008 (Ministry of Agriculture) | Agriculture, fisheries, veterinary, economics | Field-day support; crop-cut assistance; farmer registry updates (accompanied) | Field-safety induction | 16 weeks with seasonal peaks matched to crop calendar | High (every upazila has all three offices) | Field kits | Farmer personal data under DAE custody | Fieldwork safety; vehicle use rules | Survey coverage; extension event counts
Local government | Union Parishads, pourashavas (330), city corporations (12), LGED offices | SRC-81; SRC-83; SRC-84; BD-GOVT-039 | All disciplines; GIS/business for LGED | Holding-tax register digitization support; facility mapping; birth-registration desk assistance | Office induction + data-handling rules | 16 weeks | Very high | Union digital centre infrastructure where available | Citizen personal data (birth/holding) restricted - digitization on authorized systems only | Personal-data exposure; political interference in placement (safeguards required) | Registers digitized; maps drafted; desk service counts
Social protection | District and upazila social welfare offices; program offices (allowance programs) | BD-GOVT-034 | Social work, sociology, development studies | Accompanied beneficiary verification; help desks; old-age home support | Safeguarding + impartiality training | 16 weeks | High | Office desks | Beneficiary lists confidential; accompanied-visit rule | Favoritism in verification; leakage enabling - dual-verification design | Verification visit logs (dual-signed); desk counts
Public infrastructure | LGED, PWD divisional offices | BD-GOVT-020; BD-GOVT-039 | Civil engineering, architecture | Condition-survey checklists; documentation organization | Technical induction | 16 weeks | Medium (divisional offices only) | Basic survey kits | No access to contract-sensitive documents | Appearance of inspection authority (must be labeled data collection) | Checklist datasets; documentation organized
Environmental services | Department of Environment offices; forest offices | BD-GOVT-017 | Environmental science, chemistry, biology | Sampling support; awareness campaigns; nursery support | Lab and field safety induction | 16 weeks | Medium | Sampling kits | Sample chain-of-custody under DoE rules | Sample tampering risks | Samples processed; campaign counts
Digital government | ICT Division; a2i; union digital centers (count needs verification - GAP-20) | BD-GOVT-010 | Computer science, EEE, MIS | Approved digitization projects; portal content; digital-literacy training for citizens | Technical project onboarding | 16 weeks | Medium-high | Workstations | Project credentials scoped to non-sensitive instances | Unauthorized system access - strict credential scope | Records digitized; training sessions delivered
Public information and records | National Archives; district record rooms; information offices | BD-GOVT-011 | Library science, history, Bangla/English | Archive box-listing; record-room organization; citizen charter drafting support | Archive handling rules | 16 weeks | Medium | Gloves, scanning equipment | Original records remain in official custody | Loss/damage of originals; misuse of personal data found in records | Boxes listed; record rooms organized
Public procurement monitoring (observer) | CPTU; procuring entity documentation cells | BD-GOVT-016 (planning); CPTU under IMED | Business, accounting, law | Bid document organization; procurement portal publication checks; archive digitization of past tenders | CPTU SOP training; MANDATORY non-evaluation MOU | 16 weeks | Low-medium (documentation cells only) | Office desks | Bid security and evaluation materials OFF-LIMITS | Perceived influence on procurement - observer role must be public and non-evaluative | Documents organized; publication timeliness checks logged
Public service delivery monitoring | Cabinet Division GRS cells; district grievance desks | BD-GOVT-003 | Development studies, statistics, social sciences | Observation surveys against citizen charters; grievance-desk support; report drafting | Instrument-specific training | 16 weeks | Medium | Survey tablets | Findings go to M&E unit under program protocol | Retaliation risk against student observers (see safeguards framework) | Survey datasets; observation reports
Research, statistics and data quality | BBS district offices; BANBEIS | BD-GOVT-016 (Statistics and Informatics Division) | Statistics, economics, data science | Authorized survey enumeration; aggregate quality checks | BBS enumerator training (where certified) | Survey windows | Medium | Survey kits | Household data under BBS confidentiality rules | Data fabrication - double-entry and spot re-interviews required | Survey records; quality-check logs
Other public institutions | Constitutional bodies (Election Commission etc.) | BD-GOVT-013 | Case-by-case | NOT recommended for routine placement (electoral integrity sensitivity); referral-only engagement | NA | NA | None | NA | Statutory confidentiality | Perceived politicization | NA

## D16 Capacity Model
Dataset 16: Hosting and Supervision Capacity Model (low/medium/high)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
capacity_item | basis | low | medium | high | unit | notes
Upazila-level office placements (495 upazila complexes) | Derived (ASM-11): 15/20/30 students per upazila per year | 7425 | 9900 | 14850 | students/year | All upazila complexes hosting simultaneously is a strong assumption; phased rollout more realistic
Union Parishad placements (4,554 unions) | Derived (ASM-12): 1/2/4 students per union per year | 4554 | 9108 | 18216 | students/year | Pairs with union digital centers where functional
Primary school placements (65,567 schools) | Derived (ASM-13): 1/2/3 students per school per year | 65567 | 131134 | 196701 | students/year | Education-sector only; head-teacher supervision capacity is the binding constraint, not building count
Secondary institutions (19,211-21,086) | Derived (ASM-13): 1/2/3 per institution | 21086 | 42172 | 63258 | students/year
NU college campus-based placements (2,260-2,500 colleges) | Derived (ASM-14): 20/50/100 per college per year | 50000 | 120000 | 250000 | students/year | College-based model where students serve near their own college - the only mechanism that can plausibly absorb 100,000+ participants
Health facilities (418 UHCs + district hospitals) | Derived (ASM-15): 8/12/20 per facility | 3800 | 5800 | 9600 | students/year | 418 UHCs + 64 district hospitals = 482 facilities
District administration placements (64 DC offices) | Derived (ASM-16): 20/40/60 per office | 1280 | 2560 | 3840 | students/year
AGGREGATE theoretical placement capacity (annual) | Sum of above rows | 155916 | 322174 | 706465 | students/year | Theoretical, NOT operational: assumes every institution type participates; real constraint is trained supervisors and coordination, verified by none of these numbers
Trained supervisors required - scenario S1 (100,000) at 1:20 | Derived (ASM-07) | 5000 | 5000 | 5000 | supervisors | Mid estimate; ratio fixed at planning default
Trained supervisors required - S2 (200,000) at 1:20 | Derived (ASM-07) | 10000 | 10000 | 10000 | supervisors
Trained supervisors required - S3 (300,000) at 1:20 | Derived (ASM-07) | 15000 | 15000 | 15000 | supervisors | Roughly equals 1 percent of the 1,464,350 filled government posts (SRC-09) - large but not absurd
Supervisor training cohort capacity | Derived (ASM-17): 25 trainees per trainer-day; 200 trainer-days/year per trainer | 5000 | 10000 | 15000 | supervisors trainable per year by 1/2/3 dedicated training units | A 30-person central training unit can certify ~15,000 supervisors/year (2-day course each)
University coordination staff (1 per 200 enrolled participants) | Derived (ASM-18) | 500 | 1000 | 1500 | staff | Across all participating universities; 173 universities exist (SRC-01)
Government program office staff (1 per 2,000 participants) | Derived (ASM-18) | 50 | 100 | 150 | staff | National + divisional + district coordination
Digital platform: concurrent placement records | Derived (ASM-19): 2 placement windows/year | 50000 | 100000 | 150000 | records live concurrently | Platform must handle registration, attendance, supervisor sign-off, grievance intake
Distinguishing vacancies from hosting capacity | Methodological note | NA | NA | NA | note | The 521,922 vacant government posts (SRC-09) represent UNFILLED JOBS, not hosting capacity. Hosting capacity depends on supervisor availability, workspace and task design - NOT on vacancy counts. This row exists to prevent a common analytical error.

## D17 Financial Model
Dataset 17: Financial Model - per-participant costs and scenario totals (BDT)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
category | cost_item | basis | low_BDT | medium_BDT | high_BDT | funding_bearer | notes
Per-participant cost | Student stipend (4 months) | BDT 3,000 / 5,000 / 8,000 per month | 12000 | 20000 | 32000 | Government | Anchors: DYD training allowance precedent BDT 4,500/month (SRC-56); private-sector internship range 10,000-15,000 (SRC-93); garment minimum wage 12,500 (SRC-92) used as upper reference
Per-participant cost | Transport allowance (4 months) | BDT 1,000 / 2,000 / 3,000 per month | 4000 | 8000 | 12000 | Government | Local bus/van commutes; away-from-home placements higher
Per-participant cost | Accommodation support (share of students placed away from home) | 40% of students x BDT 2,000-4,000/month | 3200 | 4200 | 6400 | Government | Medium: 35% x BDT 3,000; low: 40% x 2,000; high: 40% x 4,000
Per-participant cost | Accident and medical insurance | Annual premium | 500 | 500 | 500 | Government | Group cover assumed; market verification needed (GAP-23)
Per-participant cost | Meal supplement (4 months) | BDT 0 / 500 / 1,500 per month | 0 | 2000 | 6000 | Government | Low scenario assumes no meal support
Per-participant cost | Orientation and student training | Per participant | 2000 | 3500 | 5000 | University + Government | 3-5 day orientation: content, venue, materials
Per-participant cost | University coordination cost | Per participant | 1000 | 1500 | 2000 | University | Academic credit administration, placement office
Per-participant cost | Host institution cost (workspace, utilities) | Per participant | 1500 | 2500 | 3500 | Government (host) | Desk space, materials
Per-participant cost | Supervisor training (amortized) | BDT 5,000-10,000 per supervisor / 20 students | 250 | 375 | 500 | Government | 2-day supervisor certification
Per-participant cost | Digital platform (annual cost / participants) | BDT 500M / 750M / 1,000M total | 1667 | 2500 | 3333 | Government | At 300,000 participants; platform costs scale sub-linearly so per-capita is higher at lower participation - see scenario totals
Per-participant cost | Monitoring, evaluation and audit | Per participant | 300 | 500 | 800 | Government | Independent M&E institution, spot audits
Per-participant cost | Program management | Per participant | 500 | 800 | 1200 | Government | Central and field administration
Per-participant cost | TOTAL per participant (at 300,000 scale) | Sum of all items | 26917 | 46375 | 73233 | Mixed | Preliminary estimate - see limitations
Scenario totals - 100,000 participants | Total annual cost (BDT) | All items x participants | 3025000000 | 5137500000 | 7990000000 | Mixed | Preliminary estimates; no claimed savings from corruption reduction are included anywhere in this model
Scenario totals - 100,000 participants | Total annual cost (BDT crore) | 1 crore = 10,000,000 BDT | 302.5 | 513.8 | 799 | Mixed
Scenario totals - 100,000 participants | Government share (approx.) | Stipend, transport, accommodation, insurance, meals, host cost, supervisor training, platform, M&E, management | 266.2 | 452.1 | 703.1 | BDT crore | Approximate split: university bears orientation share and coordination cost
Scenario totals - 100,000 participants | University share (approx.) | Orientation share + coordination | 36.3 | 61.6 | 95.9 | BDT crore | Public universities would require UGC funding lines; private universities cost-sharing decisions required
Scenario totals - 100,000 participants | Cost per completed placement (BDT) | Total / assumed 90% completion | 33611 | 57083 | 88778 | BDT | Completion-rate assumption ASM-20; AmeriCorps completion target 89% (SRC-68) used as international reference
Scenario totals - 100,000 participants | One-time setup costs (Year 1 additional) | Platform build, pilot design, legal drafting, institutional agreements | 2000000000 | 3500000000 | 5000000000 | BDT | Rough order of magnitude; refining requires vendor quotes and legal cost analysis (GAP-23)
Scenario totals - 200,000 participants | Total annual cost (BDT) | All items x participants | 5550000000 | 9525000000 | 14980000000 | Mixed | Preliminary estimates; no claimed savings from corruption reduction are included anywhere in this model
Scenario totals - 200,000 participants | Total annual cost (BDT crore) | 1 crore = 10,000,000 BDT | 555 | 952.5 | 1498 | Mixed
Scenario totals - 200,000 participants | Government share (approx.) | Stipend, transport, accommodation, insurance, meals, host cost, supervisor training, platform, M&E, management | 488.4 | 838.2 | 1318.2 | BDT crore | Approximate split: university bears orientation share and coordination cost
Scenario totals - 200,000 participants | University share (approx.) | Orientation share + coordination | 66.6 | 114.3 | 179.8 | BDT crore | Public universities would require UGC funding lines; private universities cost-sharing decisions required
Scenario totals - 200,000 participants | Cost per completed placement (BDT) | Total / assumed 90% completion | 30833 | 52917 | 83222 | BDT | Completion-rate assumption ASM-20; AmeriCorps completion target 89% (SRC-68) used as international reference
Scenario totals - 200,000 participants | One-time setup costs (Year 1 additional) | Platform build, pilot design, legal drafting, institutional agreements | 2000000000 | 3500000000 | 5000000000 | BDT | Rough order of magnitude; refining requires vendor quotes and legal cost analysis (GAP-23)
Scenario totals - 300,000 participants | Total annual cost (BDT) | All items x participants | 8075000000 | 13912500000 | 21970000000 | Mixed | Preliminary estimates; no claimed savings from corruption reduction are included anywhere in this model
Scenario totals - 300,000 participants | Total annual cost (BDT crore) | 1 crore = 10,000,000 BDT | 807.5 | 1391.2 | 2197 | Mixed
Scenario totals - 300,000 participants | Government share (approx.) | Stipend, transport, accommodation, insurance, meals, host cost, supervisor training, platform, M&E, management | 710.6 | 1224.3 | 1933.4 | BDT crore | Approximate split: university bears orientation share and coordination cost
Scenario totals - 300,000 participants | University share (approx.) | Orientation share + coordination | 96.9 | 166.9 | 263.6 | BDT crore | Public universities would require UGC funding lines; private universities cost-sharing decisions required
Scenario totals - 300,000 participants | Cost per completed placement (BDT) | Total / assumed 90% completion | 29907 | 51528 | 81370 | BDT | Completion-rate assumption ASM-20; AmeriCorps completion target 89% (SRC-68) used as international reference
Scenario totals - 300,000 participants | One-time setup costs (Year 1 additional) | Platform build, pilot design, legal drafting, institutional agreements | 2000000000 | 3500000000 | 5000000000 | BDT | Rough order of magnitude; refining requires vendor quotes and legal cost analysis (GAP-23)

## D18 Legal Framework
Dataset 18: Legal and Institutional Feasibility Register (15 instruments)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
legal_id | instrument | instrument_type | verification_status | substance | current_status | relevance_to_proposed_program
LEG-01 | National Service Ordinance, 1970 (Ordinance No. XXII of 1970) | Ordinance (pre-independence, Pakistan era, made under the Proclamation of 25 March 1969) | Verified - full official text read (bdlaws.minlaw.gov.bd act-details-361); SRC-46 | COMPULSORY MILITARY national service: every male citizen aged 18-20 with matriculate or higher education renders 1 year of service in the Bangladesh Army, Navy or Air Force (s.3, s.5(4)); reserve liability to age 35 with 15-30 day annual refresher training (s.6-7); students may be deferred (s.4); medical/engineering/veterinary students exemptible (s.3(4)(b)) | Section 1(3): comes into force only on a day the Government appoints by Gazette notification. No commencement notification identified in this research; one legal inventory lists the Ordinance as repealed (SRC-48); the Validation of Laws Act 1975 preserved pre-1971 laws generally. Status: DORMANT at best, possibly repealed - formal legal confirmation required (GAP-24) | NO direct legal authority for the proposed program: (a) it is a military service instrument, not a civilian university semester; (b) male-only coverage conflicts with constitutional equality guarantees (Art. 27-28); (c) it has never been brought into operation. A modern civilian program requires NEW legislation; this Ordinance should not be relied upon
LEG-02 | University Grants Commission of Bangladesh Order, 1973 (President's Order No. 10 of 1973) | Presidential Order - operative statute | Verified - official text read (bdlaws act-details-449/446); SRC-49 | UGC frames higher-education development plans, determines and allocates funds to universities, evaluates programmes, collects statistics, advises Government on new universities, and may visit universities (s.5); if a university fails to comply with a UGC recommendation, UGC may WITHHOLD GRANTS (s.5(3)); appeals lie to the President (s.13) | In force | UGC has FINANCIAL leverage (grant conditionality) but curriculum authority rests with each university's statutory bodies (senate/academic council under the respective university acts). A compulsory service semester could be driven through: (i) UGC grant conditions, (ii) UGC recommendations backed by withholding power - both slower and softer than direct mandate; statutory amendment remains the clean route
LEG-03 | Private Universities Act, 2010 | Act of Parliament - operative | Partially verified - requirement that a private university's educational programme plan be approved by UGC confirmed via legal analysis (SRC-51) and UGC enforcement actions against unapproved programs (SRC-04-cited reporting); exact section numbers require the statute text (GAP-25) | Private universities operate under UGC-approved programme plans; UGC has repeatedly identified universities running unapproved courses | In force | Private universities cannot unilaterally add a compulsory service semester to degree requirements without UGC-approved programme plan amendment; conversely a UGC-driven standard would reach private universities through this approval mechanism
LEG-04 | National University Act, 1992 | Act of Parliament - operative | Verified via commonlii text + gazette PDF (SRC-50) | NU is the affiliating university for graduate/honours/postgraduate colleges; it prescribes courses and examinations for affiliated colleges | In force | Because any 100,000+ program structurally requires NU college participation (see PL-15), NU's course and examination regulations are the SINGLE most important curriculum gateway; NU academic council approval plus UGC concurrence would be needed
LEG-05 | Individual public university acts (University of Dhaka Order 1973, and successors) | Each public university has its own statute | Established structure; per-act verification not performed this phase (GAP-25) | Academic councils and senates regulate courses of study, examinations and degrees | In force | Each public university would need its own academic council/senate decision OR an umbrella statutory change; 63 public universities x individual processes = years of sequential approvals unless Parliament legislates uniformly
LEG-06 | Constitution of the People's Republic of Bangladesh, Article 21 | Constitutional provision | Verified - official text (SRC-54) | Art. 21(1): duty of every citizen to observe the Constitution and laws, maintain discipline, perform public duties and protect public property; Art. 21(2): duty of persons in the service of the Republic to strive to serve the people | In force | Provides a constitutional VALUES anchor for voluntary/curricular service but imposes no enforceable individual service obligation on students; cannot alone mandate a semester
LEG-07 | Constitution, Articles 27 and 28 (equality; non-discrimination on grounds including sex) | Constitutional provision | Verified - official text index (SRC-54) | Equality before law; no discrimination on grounds of sex etc. | In force | Any compulsory service design MUST be gender-neutral and equality-compliant - reinforcing the conclusion that the male-only 1970 Ordinance is unusable
LEG-08 | Right to Information Act, 2009 | Act of Parliament | Verified - full official text (SRC-31, Phase 1) | Citizens may request information from public authorities; designated information officers; 20-working-day response | In force | Enables the transparency backbone of the program: students can lawfully request published procedures, standards and statistics relevant to service monitoring; also the model for institutional information disclosure
LEG-09 | Disclosure of Public Interest Information (Protection) Act, 2011 (whistleblower protection) | Act of Parliament | Verified - official text located (SRC-52) | Protects persons who disclose public-interest information from retaliation; duties of authorities receiving disclosures | In force | Critical safeguard layer for students who observe irregularities and report through authorized channels; students should be mapped into this Act's protection framework explicitly in program rules
LEG-10 | Anti-Corruption Commission Act, 2004 | Act of Parliament | Verified - English translation (SRC-53) | ACC inquiry/investigation powers; special powers in corruption investigations | In force | Students have NO ACC powers; the program's referral pathway routes credible flags to supervisors, department heads, or the ACC's public complaint channels - never to student-led investigation
LEG-11 | BMDC rotatory internship rules (medical) | Professional council regulation | Verified - official BMDC PDF (SRC-94) | One-year rotatory internship is a prerequisite for BMDC registration | In force | Medical students' service designs must integrate with, not duplicate, the existing compulsory internship; MBBS internship itself could be RECOGNIZED as partially satisfying a service semester (a zero-cost alignment option)
LEG-12 | Bangladesh Labour Act, 2006 (applicability question) | Act of Parliament | NOT analyzed this phase - preliminary interpretation only | Whether credit-bearing mandatory student placements constitute employment (wage/hours rules) is unresolved | In force (for employees) | Preliminary interpretation: academic credit placements supervised by universities are typically not employment relationships; formal legal advice required before scale-up; misclassification risk = program-wide liability (GAP-26)
LEG-13 | Public procurement framework (Public Procurement Act and Rules) | Act + Rules | NOT analyzed this phase (GAP-26) | e-GP procurement; CPTU oversight | In force | Only relevant to (a) the program's own procurement of platform/training services and (b) the strict boundaries of student observer roles in procurement monitoring
LEG-14 | National Service Programme (2010, administrative) | Government program under Ministry of Youth and Sports / Department of Youth Development | Verified via news + ministry-linked reporting (SRC-55; SRC-56) | Administrative (non-statutory) program since 2009-10: training then up to 2 years of placement in government offices for unemployed youth, expanded across upazilas in 2016; monthly allowances in the few-thousand-taka range | Operational at program level (scale and current status require verification - GAP-26) | DIRECT DOMESTIC PRECEDENT: Bangladesh already places youth in government offices under an administrative program - evidence that host placements are administratively feasible WITHOUT new primary legislation for a PILOT; but a COMPULSORY degree requirement needs statute
LEG-15 | University academic calendar disruption risk (session jam) - feasibility context | Not a legal instrument; operational constraint | Verified reporting (SRC-97) | Public universities routinely run multi-year session delays; COVID pushed completion beyond 5 years in some programs | Ongoing | Any model that ADDS a semester lengthens time-to-degree and compounds session jam; redesign must SUBSTITUTE existing credits/terms rather than append time

## D19 International
Dataset 19: International Comparison - 6 verified programs
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
model_id | program_name | country | responsible_institution | target_participants | mandatory_status | duration_and_structure | funding_model | placement_structure | scale | outcomes_measured | documented_problems_limitations | lessons_for_bangladesh
INT-01 | Kuliah Kerja Nyata (KKN) - Student Study Service | Indonesia | Individual universities under national Tridharma policy (community service as the third duty of higher education beside teaching and research) | University students (undergraduate, most state universities) | Mandatory at most state universities (institution-level policy); institutionalized in higher education system since 1973 (SRC-57; SRC-59) | About 4-8 weeks of field residence in a village/community (UGM model: 7-8 weeks; SRC-57); credit-bearing (typically 2-6 credits, varies by university) | Government + universities; student living costs largely borne by students/university programs | Batch placement in villages; teams with field supervisor (dosen pembimbing) | UGM alone sends 6,000-7,000 students yearly to 400+ villages (SRC-58); KKN-PPM lineage since 1951 at UGM | Program evaluation literature exists (efficacy studies); NO rigorous evidence of corruption reduction | Variation in quality between universities; supervision intensity varies; documented as effective for civic learning | CLOSEST STRUCTURAL MODEL: community-embedded, credit-bearing, in-degree. Demonstrates a Muslim-majority developing Asian democracy running service semesters at national scale for 50+ years. Scale per university is thousands, not tens of thousands
INT-02 | National Service Training Program (NSTP) | Philippines | Commission on Higher Education (CHED) + TESDA + DND, under Republic Act No. 9163 (2001) | ALL male and female college students in any bachelor or technical-vocational program | Mandatory; students choose one of three components (CWTS civic welfare, LTS literacy teaching, ROTC military training) | Two semesters x 54 training hours = 3 academic units total (SRC-61; SRC-62) | Government-funded special scholarship program for qualified NSTP students; delivered through institutions | Campus-based training with community application components | Covers the entire national tertiary cohort structurally (component choice-based) | Graduates enter the National Service Reserve Corps; annual evaluations by CHED | NO rigorous evidence of corruption reduction; ROTC has faced documented hazing/governance problems historically | MOST RELEVANT LEGAL DESIGN: a national statute mandating a credit-bearing service component across all tertiary institutions - the template for what Bangladesh would need to legislate; also a cautionary tale on component choice and quality control
INT-03 | National Youth Service Corps (NYSC) | Nigeria | Federal Government scheme (Decree No. 24 of 22 May 1973, now Act) | Graduates of universities and polytechnics below age 30 | Mandatory for graduation/certification (one-year post-tertiary) | 1 year: orientation camp (3 weeks, reformed to 6 weeks in 2026) + Place of Primary Assignment (full-time work) + weekly Community Development Service | Substantial federal budget: 2022 allocation about N12.17 billion for kits/transport/feeding; corps members receive monthly allowance; budget strain documented | Individual deployment to schools, hospitals, government offices nationwide; posting AWAY from home state | From 2,364 corps members (1973-74) to about 400,000 mobilized annually; 650,000 target for 2026 if resources permit (SRC-64) | Scheme-scale comparable to the 300,000 hypothesis; long-running (50+ years) | DOCUMENTED PROBLEMS: certificate fraud and forged exemption certificates (Kemi Adeosun 2018 resignation case - SRC-65); certificate racketeering convictions by ICPC; budget constraints; security incidents | SCALE PROOF: Nigeria sustains ~400,000 annual mobilization. ALSO THE CENTRAL WARNING: the scheme itself became a corruption object (certificate fraud) - any Bangladeshi program MUST design verification, digitization and audit from day one or replicate NYSC's failure modes
INT-04 | National Service Scheme (NSS) | India | Ministry of Youth Affairs and Sports, Government of India | College and +2 level students | VOLUNTARY enrollment | Typically 2 years, 240 hours of community service each year alongside study | Government-funded (central + state shares); volunteers not paid wages | Campus-based units (each 100 volunteers) with program officers; regular + special camping | Launched 1969 in 37 universities with 40,000 volunteers; now spread over 771 universities and 51+ councils (official - SRC-66); about 3.65 million volunteers in ~39,695 units (SRC-67) | Official ministry reporting; scholarly evaluations of civic outcomes exist | Voluntary nature limits scale; quality varies by unit | VOLUNTARY ALTERNATIVE EVIDENCE: a neighboring South Asian democracy operates campus service units at multi-million scale voluntarily - relevant if Bangladesh tests voluntary uptake before any mandate
INT-05 | AmeriCorps (incl. AmeriCorps State and National, VISTA, NCCC, AmeriCorps Seniors) | United States | Federal agency (AmeriCorps) | Adults 17+ (members); seniors for AmeriCorps Seniors | Voluntary, paid national service | Full-time or part-time service terms (typically 10-12 months) | Federal agency budget (over USD 1 billion annually) covering living allowances, education awards (Segal); FY22 evaluation budget USD 4.12 million (SRC-69) | Placement with nonprofit, school, public agency and community partners | More than 200,000 AmeriCorps members and AmeriCorps Seniors volunteers placed annually (SRC-68) | Agency annual performance reports, independent audits, Results for America evidence tiers; completion target 89% | Documented variation in member experience; periodic congressional scrutiny | PROFESSIONALIZED MODEL: paid members, contract-like terms, independent evaluation and audit infrastructure - the governance benchmark for program integrity (living allowance, grievance systems, data systems) that a large Bangladeshi program would need
INT-06 | Service National Universel (SNU) | France | State (Ministry of National Education and Youth) | Teenagers (15-16 cohort initially targeted) | VOLUNTARY (universal compulsory ambition deferred after public debate) | Phase 1: 2-week cohesion stay; Phase 2: at least 84 hours (12 days) of service engagement (SRC-70; SRC-71) | State-funded; free for participants | Residential then individual placement in civil or military facilities | Voluntary cohorts; 2019 reporting projected 800,000/year IF made universal (SRC-72) | Government-commissioned scenario studies (2025 strategie-plan note exploring voluntary vs compulsory, civil vs military axes) | Voluntary take-up far below universal ambitions; cost and logistics of compulsion contested | DELIBERATION PRECEDENT: even a G7 state paused before mandating national service, moving voluntary-first while studying four scenarios - supporting a pilot-then-decide pathway for Bangladesh

## D20 Anti-Corruption
Dataset 20: Anti-Corruption Mechanisms (AC-01 to AC-09) and Safeguards (SG-01 to SG-06)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
mechanism_id | mechanism | existing_problem_or_risk | student_permitted_role | responsible_supervision | evidence_collected | independent_verification | referral_or_escalation_process | expected_outcome | limitations
AC-01 | Service delivery monitoring against published standards | Services diverge from published citizen charters (times, fees, documents required); citizens lack structured feedback channels | Structured observation of service points against the charters already published; recording of actual waiting times, steps and informal demands using pre-approved instruments | Host office supervisor (e.g., service delivery focal point); program M&E unit aggregates anonymized data | Observation logs; time-and-motion records on sampled services | 10% re-observation by independent program staff; dataset cross-checks vs office registers | Patterns reported to the host department head and program M&E unit through standard reporting, not public accusation | Management-level process fixes; charter revisions; focused inspections | Cannot attribute individual misconduct; observation changes behavior while observed (Hawthorne effects); must never be used for individual performance accusations
AC-02 | Documenting delays and procedural bottlenecks | Administrative delays create opportunities for speed-money demands | Process-tracking of complete citizen journeys (application to delivery) with timestamps from official registers | Supervising officer certifies register extracts | Delay distributions per service per office | Cross-verification against office dispatch registers; office-level aggregation only | Bottleneck reports to department management and, in aggregate, to the Cabinet Division GRS | Decongestion of identified steps; service standard revisions | Students must never confront staff; individual blame assignment is outside program scope
AC-03 | Improving completeness of public records | Registers are incomplete/outdated, which enables ghost entries and manipulation | Assisted digitization and completeness checks of NON-SENSITIVE registers (asset registers, library catalogues, archive box lists) | Custodian officer retains data custody; students perform data entry and completeness flags | Volume digitized; completeness percentages; flagged gaps | Double-entry and sampling re-checks by program QA | Gap reports to record custodian | Complete, queryable registers that shrink space for manipulation | No access to personal/confidential files; digitization scope fixed by MOU
AC-04 | Supporting authorized digitization projects | Paper-based processes reduce audit trails | Batch execution of approved digitization task lists (indexing, OCR cleanup, metadata) | Government project owner under ICT Division/a2i governance | Records digitized with error rates | Project QA per e-governance standards | Standard project reporting | Faster, audit-friendly digital services | Students work on authorized instances only; credentials scoped; no independent database administration
AC-05 | Identifying inconsistencies in administrative AGGREGATE data | Aggregate statistics (attendance, stock, output) may contain inconsistencies detectable by systematic comparison | Arithmetic and cross-source consistency checks on PUBLISHED aggregate datasets | Program M&E unit + host office analyst | List of inconsistencies (e.g., totals not matching components) | Independent recomputation by program analysts | Inconsistency memos to the publishing office with request for correction | Corrected statistics; improved data discipline | Aggregate analysis only - no individual-level records; errors may be innocent; tone must be non-accusatory
AC-06 | Recording service delivery outcomes | Outcomes of public programs are under-documented | Structured follow-up calls/visits on sampled service beneficiaries using authorized instruments | Host program office (e.g., social welfare) | Outcome datasets (benefit received, timeliness) | Supervisor validation of a sample | Program-level outcome reports | Evidence base for program improvement and budget decisions | Beneficiary privacy protected; contact data used only for authorized follow-up
AC-07 | Helping citizens understand published procedures and requirements | Information asymmetry forces citizens to rely on brokers | Citizen help desks; RTI application assistance; plain-language rewrites of citizen charters | Office-in-charge of the help desk | Citizens assisted; RTI applications filed (a transparency multiplier) | Desk logs | Desk throughput audit | Reduced broker dependence; more RTI-driven disclosure | Strict neutrality; no individual case advocacy against officials
AC-08 | Supporting independent evaluation of public services | Independent eyes-on-ground capacity is scarce at scale | Students as survey/enumeration workforce for INDEPENDENT evaluations commissioned from universities or research institutes (not from the evaluated office) | Independent evaluator (university/research institute) - NOT the evaluated office | Evaluation datasets | Standard survey QA (back-checks, re-interviews) | Evaluation reports with program governance | Independent performance evidence feeding reform | Chinese walls required between student placement office and evaluation unit to avoid conflicts of interest
AC-09 | Referring suspected misconduct through authorized channels | Irregularities observed in the field currently lack safe, structured referral pathways | Students NEVER investigate; where a student incidentally observes apparent misconduct, the program provides a confidential referral form routed to the program's protection officer, who may refer to department heads, the ACC public complaint channel, or the whistleblower framework under the 2011 Act | Program protection officer (designated); ultimate recipients: department head / ACC / PIDA 2011 channels | Referral records (anonymized statistics only) | Program-level referral logs reviewed by oversight committee | Referral to authorized bodies with student identity protected | Cases enter official processes with proper protection | Students must not be tasked to find misconduct; retaliation-prevention protocols mandatory; false-accusation safeguards (documentation standards) required
SG-01 | Safeguard - student protection from retaliation | Students placed inside offices they observe face pressure risks | PIDA 2011 coverage extended explicitly to program participants; program protection officer; anonymous grievance channel; no student is ever required to confront wrongdoers; placement rotation | Program protection officer + PIDA framework | Grievance and retaliation-incident statistics | Independent oversight committee reviews all retaliation complaints | Immediate escalation + placement transfer | Students protected; program credibility maintained | Protection is only as strong as enforcement - independent oversight body with teeth is essential
SG-02 | Safeguard - privacy and personal data | Registrars contain citizen personal data; students could be exposed to or leak it | Data-access MOUs per placement; no personal files; aggregate/de-identified tasks only; data-handling oath; breach protocol | Host data custodian + program data office | Data-handling compliance; breach incidents | Quarterly data-compliance audits | Breach protocol triggers investigation | Citizen privacy preserved; program trust maintained | Cultural enforcement required beyond rules - supervision is the real control
SG-03 | Safeguard - impartiality and political neutrality | Placements could be politicized; students could be drawn into partisan activities | Charter of student conduct: no political activity during placement; placements allocated by transparent algorithm (merit + field of study + quota policy); no placement in the student's own family's constituency of influence where avoidable | Program charter + university registrars | Charter breaches; placement-allocation audits | Allocation-log audit by oversight committee | Charter violations trigger removal | Neutrality preserved | Complete insulation impossible; transparency of allocation rules is the practical mitigation
SG-04 | Safeguard - conflicts of interest | Students placed where relatives work or where they have personal stakes could be compromised or exploited | Mandatory declaration of relatives in host institution; automatic re-allocation on declared conflicts | University placement office | Declared conflicts; re-allocations | Random conflict-declaration audits | Re-allocation executed | Conflict-free placements | Under-declaration risk remains; audits deter
SG-05 | Safeguard - protection against false accusations | Students could fabricate service records or make unfounded accusations; offices could falsely accuse students | Every finding requires documentary basis + supervisor co-signature; fabrication is a disciplinary offense with academic consequences; digital attendance + task logs reduce fabrication space | University + program office jointly | Fabrication cases detected | Double-entry, spot checks, digital logs | Disciplinary process | Integrity of program data maintained | Must not chill legitimate observations - the evidentiary bar should be documented but reasonable
SG-06 | Safeguard - anti-fraud design of the program itself (NYSC lesson) | The NYSC experience shows a large service scheme can itself become a corruption object (certificate fraud, ghost participants) | Digital completion certificates with QR verification; biometric or digital attendance; independent spot audits; publication of aggregate participation statistics | Program office + independent auditor | Verified-completion rates; audit findings | External audit (Chartered accountants + CAG-style oversight) | Audit findings to oversight committee and, where warranted, ACC | Program integrity; certificate credibility | Constant vigilance - every verification layer can be attacked; audit rotation and data forensics needed

## D21 Risk Register
Dataset 21: Implementation Risk Register (16 risks)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
risk_id | risk_category | risk_description | likelihood | impact | mitigation_and_safeguards
RSK-01 | Education disruption | Adding a semester or field term displaces coursework, worsens session jam (already multi-year in some programs - SRC-97), and delays graduation | High | High | Mandatory SUBSTITUTE-not-add design: service credits replace existing elective/practicum credits; program duration neutral by design; per-program academic council sign-off; monitor time-to-degree as a core M&E indicator
RSK-02 | Graduation delay | Even a neutral design can delay students if placements are scarce or scheduling conflicts with exams | Medium | High | Two placement windows per year; guaranteed-placement rule (university cannot require service without confirmed placement); summer-window flexibility
RSK-03 | Unequal burden on low-income students | Stipend below real costs blocks poorer students; away-from-home placements cost more | High | High | Needs-based top-up stipends; placement near home college as default (NU college model); transport/accommodation support lines; fee-waiver equivalents
RSK-04 | Exploitation of unpaid/underpaid student labor | Hosts may treat students as free clerical labor with no learning value; a 300,000-student cohort at sub-minimum stipends is a labor-market distortion | High | High | Task catalogues defined by MOU (no routine backlog clearing); learning-outcome requirements per placement; host-quality scoring; stipend floors indexed to minimum wage (BDT 12,500/month garment floor - SRC-92); university audits of placement quality
RSK-05 | Political interference in placements | Placement allocation could be captured politically; ruling-party pressure on host offices | Medium | High | Algorithmic allocation with published rules; oversight committee with opposition/civil-society representation; appeal channel; allocation-log transparency
RSK-06 | Favoritism in assignments | Desirable placements sold or granted to connected students | Medium | Medium | Central matching system; conflict-of-interest declarations; randomized audit of allocation outcomes
RSK-07 | Student harassment or retaliation | Power asymmetry inside offices; retaliation against students who log irregularities | Medium | High | PIDA 2011 mapping (SG-01); protection officer; anonymous grievance channel; fast transfer mechanism; zero-tolerance protocol
RSK-08 | Misuse of personal information | Students handling citizen data could leak or misuse it; hosts could misuse student personal data | Medium | High | Data MOUs; de-identified tasks; data-handling oaths; breach protocol (SG-02)
RSK-09 | Inadequate supervision | 1:20-1:30 ratios collapse into no supervision; supervisors lack time/skills; 15,000 trained supervisors is a system-building effort in itself | High | High | Supervisor certification + workload recognition in ACRs; ratio floors by task risk; program inspectors; phase gates that do not expand faster than supervisor pipeline
RSK-10 | Administrative overload of host institutions | Government offices already carry 521,922 vacant posts (SRC-09); absorbing students without dedicated support degrades both service and placement quality | High | Medium | Dedicated program liaison posts; no-placement-without-liaison rule; batching with academic calendars; realistic scenario sizing (the 100,000 path before 300,000)
RSK-11 | Duplicate or fabricated service records | Paper-based completion verification invites fraud (NYSC certificate fraud precedent - SRC-65) | Medium | High | Digital completion records with QR verification; biometric/digital attendance; independent spot audits (SG-06)
RSK-12 | Corruption within the program itself | Stipend skimming, ghost participants, placement-selling, equipment theft | Medium | High | Treasury-direct stipend payments to student mobile accounts; published participant statistics; external audit; ACC referral pathway; whistleblower protection for program staff too
RSK-13 | Excessive public expenditure | Costs above estimates; program persists despite failing evaluation | Medium | Medium | Phase gates with pre-registered kill/continue criteria; independent evaluation BEFORE each expansion; sunset clauses for funding
RSK-14 | Poor-quality or meaningless placements | Quantity targets (300,000) drive fake placements - students present but unused; reputational collapse | High | High | Output-based completion standards; host-institution satisfaction + student experience surveys; publish placement-quality indices; penalize hosts with quality scores below floor
RSK-15 | Constitutional/legal challenge | A compulsory requirement enacted weakly (e.g., relying on the dormant 1970 Ordinance) could be struck down | Medium | High | Clean new primary legislation for any compulsory element; pilots on voluntary/credit-elective basis under existing university autonomy; Ministry of Law vetting at design stage
RSK-16 | Retaliation-driven misreporting | Hosts under monitoring pressure could intimidate observers or falsify registers ahead of observation rounds | Medium | Medium | Unannounced observation windows; rotation; triangulation across offices; trends analyzed at aggregate level

## D22 M&E Framework
Dataset 22: Monitoring and Evaluation Indicators (19 indicators)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
indicator_id | indicator_type | indicator | definition_or_measure | data_source | frequency | baseline_and_targets_notes
OUT-01 | Output | Students enrolled in service component | Count of registered students per intake | University records | Per intake | Baseline zero at start; targets set per phase
OUT-02 | Output | Students successfully placed | Placement confirmed + commenced (share of enrolled) | Program placement system | Per intake | Placement rate target 95%+ (guaranteed-placement rule RSK-02)
OUT-03 | Output | Completion rate | Students completing all service + academic requirements (share of placed) | Digital completion records | Per cohort | International reference: AmeriCorps 89% completion target (SRC-68)
OUT-04 | Output | Cost per completed placement | Total program cost / completed placements | Program financial system | Annual | Compare across phases; falling unit cost = scale efficiency
OUT-05 | Output | Supervisor coverage | Certified supervisors per 20 active students | Program HR records | Quarterly | Floor: 1:20; task-risk ratio floors per sector mapping
OUT-06 | Output | Grievance intake and resolution time | Median days to resolve student grievances | Grievance system | Quarterly | Resolution target 30 days
PRO-01 | Process | Academic performance and graduation delay | Time-to-degree of participants vs matched non-participants | University academic records | Annual | KEY INTEGRITY METRIC: program must be duration-neutral (RSK-01); matched-comparison design
PRO-02 | Process | Student expenses vs support | Net out-of-pocket cost distribution of participants | Student surveys | Per cohort | Must not burden low-income students (RSK-03)
PRO-03 | Process | Host institution satisfaction | Structured host ratings of placement usefulness | Host surveys | Per cohort | Low scores trigger host-quality review
PRO-04 | Process | Supervisor workload | Supervisor-reported hours per student; burnout indicators | Supervisor surveys | Per cohort | Detects ratio collapse (RSK-09)
PRO-05 | Process | Safety incidents | Injury, harassment, retaliation incidents per 1,000 students | Protection office + insurance claims | Quarterly | All retaliation incidents trigger review by oversight committee
EFF-01 | Service effectiveness | Processing times for selected public services | Median service delivery time at participating vs comparison offices | Service registers + AC-02 tracking | Semi-annual | Pre-registered service list; offices without placements as comparison group
EFF-02 | Service effectiveness | Records completeness and digitization | Share of target registers digitized and complete; error rates | Program QA (AC-03/AC-04) | Semi-annual | Double-entry verification
EFF-03 | Service effectiveness | Complaints and their resolution | GRS complaints per office; resolution rates; citizen satisfaction pulses | GRS data + citizen pulse surveys | Semi-annual | Interpretation requires care: rising complaints may reflect trust, not deterioration
GOV-01 | Governance outcome | Documented irregularities and verified outcomes | Number of internally flagged inconsistencies (AC-05) AND their independent verification outcomes | Program M&E + oversight committee | Annual | NEVER use allegation counts as a standalone corruption measure - report only with verification outcomes
GOV-02 | Governance outcome | Data quality of host statistics | Error rates in host-published aggregates over time | AC-05 consistency checks | Annual | A leading indicator of administrative discipline
IMP-01 | Impact (long-term) | Public service quality trend | Composite index of charter compliance across participating offices | Independent evaluation unit | Every 2 years | Attribution requires phased/matched design (Section 12 of report)
IMP-02 | Impact (long-term) | Civic outcomes of participants | Participant vs non-participant civic engagement trajectories | Longitudinal surveys (independent) | Every 3 years | KKN literature shows civic learning gains; Bangladesh evidence to be built
IMP-03 | Impact (long-term) | Graduate employability | Employment rates and time-to-first-job of participants vs matched peers | Tracer studies | Every 3 years | Secondary objective but politically important

## D23 Phased Plan
Dataset 23: Phased Implementation Model (PH-0 to PH-4 with decision gates)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
phase_id | phase_name | duration | annual_cohort_size | scope_and_activities | entry_and_exit_criteria | decision_gate
PH-0 | Design and legal preparation | 12 months | 0 (design only) | Ministry of Education + UGC + Cabinet Division working group; drafting of primary legislation for the compulsory element (voluntary pilot under existing university autonomy); MOU templates; task catalogues; digital platform specification | Entry: political decision to explore; Exit: legislation drafted, platform procured, 10-15 universities and 5 upazilas signed up | Decision gate 0: Ministry of Law confirms legal route (new statute for mandate; pilots on voluntary/credit-elective basis)
PH-1 | Voluntary pilot | 2 academic years | 5,000-10,000 students per year | 10-15 universities (mix: public direct, private, NU colleges in 3-4 districts) + host offices in 5 upazilas; voluntary enrollment in a credit-bearing service module; all safeguards live (protection officer, grievance, data MOUs) | Entry: Gate 0 passed; Exit criteria: completion rate 85%+, no unresolved retaliation cases, duration-neutrality verified (no graduation delay vs matched peers), cost within 150% of medium estimate | Decision gate 1: independent evaluation published; expansion only on evidence
PH-2 | Controlled expansion | 2 academic years | 50,000 students per year | 60+ universities across 8 divisions; NU college model begins (college-based placements near home); supervisor pipeline scaled to 2,500+; platform stress-tested | Entry: Gate 1 passed; Exit criteria: completion 87%+, placement rate 95%+, unit cost declining, zero systemic data breaches | Decision gate 2: second independent evaluation; Treasury commitment for full scale
PH-3 | National scale-up | 3 academic years | 100,000-200,000 per year | All divisions; full sector coverage; NU colleges carry the majority of volume; supervisor corps 5,000-10,000; quarterly public reporting of participation and quality indices | Entry: Gate 2 passed; Exit criteria: sustained quality indices, fraud controls verified by external audit | Decision gate 3: parliamentary review of the first 5 years; final decision on the 300,000 question
PH-4 | Target-scale operation (conditional) | Open-ended | Up to 300,000 per year | Only if Gates 1-3 all passed AND the capacity model (CSV 16) is validated by actual phase 3 data: this target REQUIRES full NU college participation (finding PL-15) and 15,000 supervisors | Entry: Gate 3 passed; standing rule: scale never expands faster than the supervisor pipeline (RSK-09) | Standing gates: annual independent audit; public dashboards; sunset review every 5 years

## D24 Assumptions
Dataset 24: Assumptions Register (ASM-01 to ASM-22)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
assumption_id | assumption | type | basis_and_sensitivity
ASM-01 | Total tertiary enrollment baseline = 4,690,876 (public system 4,362,187 + private 328,689, 2020) | SRC-05 | The most recent year with a verified all-sector total; enrollment has likely changed since 2020 - sensitivity of pipeline findings to a +/- 10% enrollment change is limited (PL-16/PL-18 shift by ~2 percentage points)
ASM-02 | Graduates/enrollment ratio indicative only (different reporting years) | Derived | Not used for any downstream calculation
ASM-03 | Students are uniformly distributed across 4 years of study | Structural assumption | REQUIRED for cohort estimates; conservative for eligibility (pass courses would SHRINK the final-year pool, making the PL-15 finding STRONGER, not weaker)
ASM-04 | 2015 public-direct and 2021 private enrollment vintages can be pooled for order-of-magnitude estimates | Derived | Both are the latest verified figures of their type; flagged in CSV 12
ASM-05 | Two placement windows per academic year (semester calendar) | Planning assumption | Matches public university two-semester system (SRC-96); NU annual colleges would need calendar adaptation
ASM-06 | Average hosting density of 10-20 students per institution | Planning assumption | No verified hosting-density data for Bangladesh (GAP-21); international programs suggest batches of 5-30 per host
ASM-07 | Supervisor ratios 1:10 / 1:20 / 1:30 as planning scenarios; 1:20 recommended default | Planning assumption | Not an established Bangladesh standard; recommended based on task-risk classification in the sector mapping
ASM-08 | Equal per-upazila / per-district distribution for scenario illustration | Planning assumption | Real allocation should follow enrollment distribution - data missing (GAP-18)
ASM-09 | Sector split percentages (Education 30%, Health 15%, Local govt 15%, Admin 10%, Digital 8%, Research 6%, Agriculture 5%, Social protection 5%, Environment 3%, Procurement 3%) | Planning assumption | Derived from verified host-network sizes (CSV 15); not a policy commitment
ASM-10 | NU college students serve near their home college | Design assumption | Required for feasibility (accommodation costs otherwise dominate); consistent with Indian NSS campus-unit model
ASM-11 | Upazila complexes host 15/20/30 students per year (low/med/high) | Planning assumption | Unverified; requires pilot data
ASM-12 | Union Parishads host 1/2/4 students per year | Planning assumption | Unverified; union digital centre functionality varies (GAP-20)
ASM-13 | Schools host 1/2/3 students per year | Planning assumption | Head-teacher supervision is the binding constraint, not buildings
ASM-14 | NU colleges host 20/50/100 students per year each | Planning assumption | The ONLY mechanism that can absorb 100,000+ participants; college capacity varies enormously (GAP-19)
ASM-15 | Health facilities host 8/12/20 students | Planning assumption | Constrained by professional council rules (BMDC alignment)
ASM-16 | DC offices host 20/40/60 students | Planning assumption | Unverified
ASM-17 | Supervisor training: 2-day course, 25 trainees per trainer-day, 200 trainer-days per trainer-year | Planning assumption | Standard training-industry planning figures
ASM-18 | Program staffing ratios: 1 university coordinator per 200 participants; 1 government program officer per 2,000 participants | Planning assumption | Comparable to large education-program staffing
ASM-19 | Digital platform costs BDT 500M-1,000M (build + annual run) | Planning assumption | Based on e-governance project cost ranges; NOT a vendor quote (GAP-23)
ASM-20 | 90% completion rate for cost-per-completion calculations | Planning assumption | Anchored to AmeriCorps 89% target (SRC-68)
ASM-21 | Stipend scenarios BDT 3,000-8,000/month | Planning assumption | Anchored: DYD allowance BDT 4,500 (SRC-56); internships 10-15k (SRC-93); minimum wage 12,500 (SRC-92)
ASM-22 | No savings from corruption reduction are counted as financial benefits | Methodological rule | Per research protocol: unsupported savings must not be presented as guaranteed benefits

## D25 Sources P3
Source Registry Phase 3 (54 new sources SRC-46 to SRC-99; combined program base: 99 sources)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
source_id | title | publisher | publication_year | url | source_type | access_date
SRC-46 | The National Service Ordinance, 1970 (Ordinance No. XXII of 1970) - full official text | Ministry of Law, Justice and Parliamentary Affairs (bdlaws.minlaw.gov.bd) | 1970 | http://bdlaws.minlaw.gov.bd/act-details-361.html | Official statute text | 2026-10-15
SRC-47 | The Pakistan National Service Ordinance, 1970 (validation note under Validation of Laws Act, 1975) | Nasir Law Site (secondary compilation) | 1970/1975 | http://nasirlawsite.com/laws/pnso.htm | Secondary legal compilation | 2026-10-15
SRC-48 | A comprehensive list of the Laws of Bangladesh (marks National Service Ordinance 1970 as Repealed) | Bangladesh Justice Audit | 2018 | https://bangladesh.justiceaudit.org/wp-content/uploads/2018/07/A-comprehensive-list-of-the-Laws-of-Bangladesh.pdf | Legal inventory (secondary) | 2026-10-15
SRC-49 | The University Grants Commission of Bangladesh Order, 1973 (P.O. No. 10 of 1973) - full official text | Ministry of Law (bdlaws.minlaw.gov.bd) | 1973 | http://bdlaws.minlaw.gov.bd/act-details-446.html | Official statute text | 2026-10-15
SRC-50 | National University Act, 1992 (full text) | CommonLII (Bangladesh legislation) | 1992 | http://www.commonlii.org/bd/legis/num_act/nua1992251 | Official statute (republished) | 2026-10-15
SRC-51 | Private univ law needs to be changed (Private Universities Act 2010 programme-approval requirement analysis) | New Age Bangladesh | 2025 | https://www.newagebd.net/post/opinion/260269/private-univ-law-needs-to-be-changed | Legal analysis (secondary) | 2026-10-15
SRC-52 | The Disclosure of Public Interest Information (Protection) Act, 2011 - official text | Ministry of Law (bdlaws.minlaw.gov.bd) | 2011 | http://bdlaws.minlaw.gov.bd/upload/act/2021-11-17-11-39-54-40.The-Dsclosure-of-Public-Interest-information-(Protection)-Act-2011.pdf | Official statute text | 2026-10-15
SRC-53 | Bangladesh Anti-Corruption Commission Act, 2004 (English translation) | U4 Anti-Corruption Resource Centre | 2004 | https://www.u4.no/assets/bangladesh-anti-corruption-commission-act-2004-english-translation.pdf | Official statute (translation) | 2026-10-15
SRC-54 | The Constitution of the People's Republic of Bangladesh (official consolidated text) | Ministry of Law (bdlaws.minlaw.gov.bd) | 1972 (consolidated) | http://bdlaws.minlaw.gov.bd/act-details-367.html | Official statute text | 2026-10-15
SRC-55 | National Service Program to expand in 64 more upazilas (program structure: training then 2-year government office placement) | Awami League party news portal (albd.org) reporting government announcement | 2016 | https://www.albd.org/articles/news/28655/National-Service-Program-to-expand-in-64-more-upazilas | News report of government program | 2026-10-15
SRC-56 | Youth Development Initiatives in Bangladesh (DYD program allowances incl. BDT 4,500/month allowance) | Scribd-published project final report | c.2016-2019 | https://www.scribd.com/document/860069901/final-report5 | Project report (secondary) | 2026-10-15
SRC-57 | Student study service / Kuliah Kerja Nyata (KKN) - program description (since 1973, Tridharma, UGM 7-8 weeks) | Wikipedia | 2026 | https://en.wikipedia.org/wiki/Student_study_service_(Indonesia) | Secondary compilation (cross-checked vs UGM page) | 2026-10-15
SRC-58 | UGM Sends Thousands of Students for Community Empowerment in 400 Villages (6,000-7,000 yearly; KKN-PPM since 1951) | Universitas Gadjah Mada (official news) | 2023 | https://ugm.ac.id/en/news/ugm-sends-thousands-of-students-for-community-empowerment-in-400-villages | Official university publication | 2026-10-15
SRC-59 | Kuliah Kerja Nyata: Student Volunteerism as... (KKN institutionalized as mandatory 1971; SSRN paper) | SSRN academic paper | 2024 | https://papers.ssrn.com/sol3/papers.cfm?abstract_id=6117466 | Academic study | 2026-10-15
SRC-60 | National Service Training Program (NSTP) - RA 9163 structure, components, coverage | Wikipedia | 2026 | https://en.wikipedia.org/wiki/National_Service_Training_Program | Secondary compilation | 2026-10-15
SRC-61 | NSTP structure: two terms x 54 training hours, 3 units (UST official page) | University of Santo Tomas (official) | 2026 | https://www.ust.edu.ph/community-development/nstp | Official university page | 2026-10-15
SRC-62 | NSTP About page (RA 9163 of 2001; components; 25-hour minimum references) | UP Diliman NSTP (official) | 2026 | https://nstp.upd.edu.ph/about-us | Official university page | 2026-10-15
SRC-63 | National Youth Service Corps (NYSC) - Decree No. 24 of 22 May 1973; mandatory post-tertiary scheme structure | Wikipedia | 2026 | https://en.wikipedia.org/wiki/National_Youth_Service_Corps | Secondary compilation (cross-checked vs nysc.gov.ng decree PDF) | 2026-10-15
SRC-64 | NYSC mobilization scale: from 2,364 (1973-74) to ~400,000 annually; 650,000 target for 2026 | Blueprint Newspapers / NTA news reports | 2026 | https://www.facebook.com/blueprint.ng/posts/nysc-to-mobilise-650000-graduates-for-service-in-2026 | News report citing NYSC Director-General | 2026-10-15
SRC-65 | Kemi Adeosun: renounce NYSC certification fraud allegations or resign (2018 resignation case); certificate fraud context | BudgIT Nigeria (civil society); Punch reporting | 2018-2026 | https://budgit.org/kemi-adeosun-renounce-the-allegations-of-nysc-certification-fraud-or-resign | Civil-society/news documentation | 2026-10-15
SRC-66 | National Service Scheme (NSS) India - official detail page (launched 1969 in 37 universities, 40,000 volunteers; now 771 universities + 51 councils) | Government of India, NSS (official) | 2026 | https://nss.gov.in/en/nss-detail-page | Official government page | 2026-10-15
SRC-67 | NSS Kerala University unit page (about 36.5 lakh volunteers in 39,695 units, 391 universities/councils, 16,278 colleges) | University of Kerala NSS (official) | 2026 | https://www.keralauniversity.ac.in/nss | Official university page (citing national data) | 2026-10-15
SRC-68 | What is AmeriCorps / About the Agency (more than 200,000 AmeriCorps members and AmeriCorps Seniors volunteers annually) | AmeriCorps (official US federal agency) | 2020-2026 | https://www.americorps.gov/about | Official government page | 2026-10-15
SRC-69 | AmeriCorps FY2026 Congressional Budget Justification (evaluations, audits, completion target 89% in Strategic Plan) | AmeriCorps (official) | 2025 | https://www.americorps.gov/sites/default/files/document/2025-06/FY%202026%20AmeriCorps%20Congressional%20Budget%20Justification.pdf | Official budget document | 2026-10-15
SRC-70 | Registration for the National Universal Service (SNU: cohesion stay + phase 2 of at least 84 hours / 12 days) | service-public.gouv.fr (official French government) | 2024 | https://www.service-public.gouv.fr/particuliers/actualites/A16926?lang=en | Official government page | 2026-10-15
SRC-71 | Service national universel (SNU) - voluntary one-month civil/military service | Wikipedia | 2026 | https://en.wikipedia.org/wiki/Service_national_universel | Secondary compilation | 2026-10-15
SRC-72 | National service: building a new French (and European) model - SNU scenario note (4 scenarios: civil/military x voluntary/compulsory) | Commissariat general de strategie et de planification (official French) | 2025 | https://www.strategie-plan.gouv.fr/files/files/Publications/2025/2025-05-04%20-%20SNU/FS-2025-Note%20Flash%20n%C2%B01-EN | Official government publication | 2026-10-15
SRC-73 | Fighting Corruption to Improve Schooling: Evidence from a Newspaper Campaign in Uganda (Reinikka & Svensson 2005, QJE/JEEA) | Quarterly Journal of Economics (author copy hosted) | 2005 | https://www.jakobsvensson.com/uploads/9/9/1/0/99107788/40004969.pdf | Peer-reviewed academic study | 2026-10-15
SRC-74 | A Replication Study of a Newspaper Campaign in Uganda (Kuecken & Jann 2019, Journal of Development Studies) | Taylor & Francis (Journal of Development Studies) | 2019 | https://www.tandfonline.com/doi/full/10.1080/00220388.2018.1506575 | Peer-reviewed replication | 2026-10-15
SRC-75 | Exposing Corrupt Politicians: The Effects of Brazil's Publicly Released Audits on Electoral Outcomes (Ferraz & Finan 2008, QJE) | Quarterly Journal of Economics (OUP) | 2008 | https://academic.oup.com/qje/article-abstract/123/2/703/1930865 | Peer-reviewed academic study | 2026-10-15
SRC-76 | Monitoring Corruption: Evidence from a Field Experiment in Indonesia (Olken 2007, JPE) | Journal of Political Economy (JSTOR/NBER) | 2007 | https://www.nber.org/papers/w11753 | Peer-reviewed academic study | 2026-10-15
SRC-77 | Social Audits and MGNREGA Delivery: Lessons from Andhra Pradesh (Afridi, Iversen & Sharan 2014, IZA DP 8095) | IZA Discussion Paper | 2014 | https://www.iza.org/publications/dp/8095/social-audits-and-mgnrega-delivery-lessons-from-andhra-pradesh | Peer-reviewed working paper | 2026-10-15
SRC-78 | Is Transparency the Best Disinfectant? A Meta-Analysis (OGP) and Kosack & Fung - Does Transparency Improve Governance? (Harvard) | Open Government Partnership / Harvard Ash Center | 2014-2018 | https://ash.harvard.edu/wp-content/uploads/2025/11/does_transparency_improve_governance_0.pdf | Meta-analysis / academic review | 2026-10-15
SRC-79 | Citizen Report Card Surveys (methodology note) | World Bank | 2000s | https://documents1.worldbank.org/curated/en/256591468780581056/pdf/286010CRC0SD0note09101public1.pdf | International institution methodology note | 2026-10-15
SRC-80 | Bangladesh Service Delivery Indicators - health (2024 publication) | World Bank | 2024 | https://openknowledge.worldbank.org/entities/publication/2e02ff15-f593-423a-bc27-146e7025d771 | International institution statistics | 2026-10-15
SRC-81 | Election FAQs: Bangladesh Local Elections May 2024 (64 zila parishads, 495 upazila parishads, 4,554 union parishads) | IFES (International Foundation for Electoral Systems) | 2024 | https://www.ifes.org/tools-resources/faqs/elections-bangladesh-2024-upazila-elections | International organization fact sheet | 2026-10-15
SRC-82 | Union councils of Bangladesh (4,585 union parishads as of 2022); current ministry count 4,580 (Prothom Alo 2026) | Wikipedia; Prothom Alo English | 2022-2026 | https://en.wikipedia.org/wiki/Union_councils_of_Bangladesh | Secondary compilation + news | 2026-10-15
SRC-83 | Municipalities of Bangladesh (330 municipalities/pourashavas) | Wikipedia | 2026 | https://en.wikipedia.org/wiki/Municipalities_of_Bangladesh | Secondary compilation | 2026-10-15
SRC-84 | List of city corporations in Bangladesh (12 city corporations, City Corporation Act 2009) | Wikipedia (list cross-checked vs LGED list) | 2026 | https://en.wikipedia.org/wiki/List_of_city_corporations_in_Bangladesh | Secondary compilation | 2026-10-15
SRC-85 | Health ministry plan to upgrade all 418 existing upazila health complexes to 101-bed facilities | The Daily Star | 2024-2026 | https://www.facebook.com/DailyStarNews/posts/the-health-ministry-has-started-implementing-its-plan-to-upgrade-all-418-ex | News report | 2026-10-15
SRC-86 | Challenges faced by medical officers (UHC and district hospital network structure, DGHS six tiers) | ScienceDirect (Heliyon) | 2024 | https://www.sciencedirect.com/science/article/pii/S2772368224000489 | Peer-reviewed study | 2026-10-15
SRC-87 | Primary School Statistics 2023: 65,567 primary schools; 384,513 teachers | Bonik Barta (citing DPE Primary School Statistics 2023) | 2024 | https://www.facebook.com/BonikBartaEn/posts/according-to-the-latest-primary-school-statistics-2023-th | News report of official statistics | 2026-10-15
SRC-88 | Bangladesh Education Statistics 2023 (21,086 institutions offering junior and secondary education) | BANBEIS, Ministry of Education | 2024 | https://objectstorage.ap-dcc-gazipur-1.oraclecloud15.com/n/axvjbnqprylg/b/V2Ministry/o/office-shed/2024/12/ | Official national statistics | 2026-10-15
SRC-89 | 19,211 government and private secondary schools including junior schools (BANBEIS current data) | Prothom Alo English (citing BANBEIS) | 2026 | https://en.prothomalo.com/youth/education/f8t5oc4rxz | News report of official statistics | 2026-10-15
SRC-90 | National University now focusing on technical and language education (NU oversees ~2,500 institutions, ~4 million students) | The Business Standard | 2025 | https://www.tbsnews.net/features/pursuit/national-university-now-focusing-technical-and-language-education | News interview with NU officials | 2026-10-15
SRC-91 | National University, Bangladesh (2,260 affiliated colleges; 555 government colleges; 881 honours colleges; second-largest university by enrollment) | Wikipedia | 2026 | https://en.wikipedia.org/wiki/National_University,_Bangladesh | Secondary compilation | 2026-10-15
SRC-92 | Bangladesh hikes minimum wage for garment workers (BDT 8,000 to 12,500/month, effective Dec 1, 2023) | Reuters | 2023 | https://www.reuters.com/world/asia-pacific/bangladesh-hikes-minimum-wage-garment-workers-after-protests-minister-2023-11 | International news agency (verified against FLA) | 2026-10-15
SRC-93 | Internship remuneration in Bangladesh typically BDT 10,000-15,000/month (private sector) | NextIntern Bangladesh / Glassdoor / professional forums | 2026 | https://www.glassdoor.com/Salaries/dhaka-bangladesh-internship-salary-SRCH_IL.0,16_IM1237_KO17,27.htm | Market data (secondary; range corroborated across sources) | 2026-10-15
SRC-94 | Rotatory Internship Programme and Logbook (1-year internship prerequisite for BM&DC registration) | Bangladesh Medical and Dental Council (official) | 2026 | https://www.bmdc.org.bd/docs/RotatoryInternshipProgramme.pdf | Official professional-council document | 2026-10-15
SRC-95 | Polytechnic Industrial Attachment Training (3-month final-year industrial attachment precedent) | BSDI (Bangladesh Skill Development Institute) | 2026 | https://bsdi-bd.org/programs/polytechnic-attachment | Training institution page (established practice) | 2026-10-15
SRC-96 | What is in an academic calendar? (public universities two-semester; private universities trimester) | The Daily Star (opinion/analysis) | 2019 | https://www.thedailystar.net/opinion/perspective/whats-academic-calendar-1530367 | News analysis (established fact) | 2026-10-15
SRC-97 | Public unis and the looming threat of session jams (chronic session delay; COVID pushed completion beyond 5 years) | The Business Standard | 2025-2026 | https://www.tbsnews.net/analysis/public-unis-and-looming-threat-session-jams-948566 | News analysis | 2026-10-15
SRC-98 | Upazila (Thana or Sub-Districts) list - 8 divisions, 64 districts, 495 upazilas | Bangladesh Data (bddata.org) | 2024 | https://www.bddata.org/db/Upazila_(Thana_or_Sub-Districts) | Data compilation | 2026-10-15
SRC-99 | Bangladesh now has 503 upazilas (gazette notification reporting) | The Daily Campus (news) | 2026 | https://www.facebook.com/thedailycampusoriginal/posts/bangladesh-now-has-503-upazilas-as-government-issues-gazette | News report of gazette | 2026-10-15

## D26 Missing Data P3
Missing-Data Register Phase 3 (12 new gaps GAP-18 to GAP-29; program total: 29 gaps)
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
gap_id | missing_dataset | description | likely_holding_authority | rti_recommended | priority | notes
GAP-18 | University enrollment by division/district | Allocation of placements by geography requires enrollment distribution; only national totals verified | UGC + BANBEIS + universities | Yes - RTI to UGC: university-wise enrollment by district for latest 3 annual reports | High | Feeds capacity model ASM-08
GAP-19 | National University enrollment by program year and course type | Final-year pool estimates (PL-09) rest on the uniform-4-year assumption; NU pass/honours/masters decomposition unpublished | National University (NU) | Yes - RTI to NU: enrollment by year of study and program type | High | Most decision-relevant single dataset for the 300,000 question
GAP-20 | Verified inventory of union digital centers and their staffing | Digital-government placement capacity (sector split assumes 8%) | ICT Division / a2i | Yes - RTI to ICT Division: functional status and staffing of union digital centers by upazila | Medium
GAP-21 | Supervision capacity: officers available for training by institution type | Hosting capacity is a guess (ASM-06, ASM-11 to ASM-16) without knowing actual officer availability | Ministry of Public Administration + Cabinet Division | Yes - RTI: sanctioned/filled posts with training function at upazila and union level | High
GAP-22 | Service-delivery baseline statistics (processing times, complaint volumes) | M&E indicators EFF-01/EFF-03 have no pre-program baseline in most offices | Cabinet Division GRS + service-providing ministries | Yes - RTI: GRS complaints and resolution statistics by office for last 3 years | High | Pre-registration of baselines before pilots is essential for attribution
GAP-23 | Program cost benchmarks (platform builds, insurance premiums, training delivery costs) | Financial model itemized but parameterized from analogues, not vendor quotes | ICT Division (platform costs); Insurance companies; NSD/NAEM (training costs) | Partial - RTI for past e-governance project costs; market quotation for insurance | Medium | Model precision improves materially with these
GAP-24 | Formal confirmation of the National Service Ordinance 1970 status (commencement notification? repeal?) | Report concludes dormant/possibly repealed from textual and inventory evidence; formal status needs Law Ministry confirmation | Ministry of Law, Justice and Parliamentary Affairs | Yes - RTI: whether any Gazette notification under s.1(3) of the 1970 Ordinance was ever issued; current validity | High | Determines whether any legacy authority exists (report concludes none usable)
GAP-25 | Section-level verification of Private Universities Act 2010 and individual public university acts | Programme-approval requirement verified via secondary legal analysis; exact sections and amendment status unverified | Ministry of Law (bdlaws full texts) | No - publicly available; task is legal research hours, not data access | Medium | Phase 4 legal drafting prerequisite
GAP-26 | Inventory of existing government internship/placement frameworks and their legal instruments | NSP (2010) scale and current status, National Internship Programme terms, circular-level rules all partially documented | Ministry of Public Administration; MY Sports (DYD); ICT Division | Yes - RTI: NSP participant numbers by year; National Internship Programme stipend terms | High | Domestic precedent sizing
GAP-27 | ACC complaint and case statistics (baseline context) | GOV-01 indicator design benefits from knowing existing complaint volumes and verification outcomes | Anti-Corruption Commission | Partial - ACC annual reports may cover; RTI for granular data | Medium
GAP-28 | Host institution physical capacity (workspace, sanitation, safety) audit | Even with officers available, buildings may not absorb batches | Cabinet Division / Ministry of Public Administration | Partial - sample RTI to selected DC offices and upazilas | Medium | Pilot design should include a physical capacity survey
GAP-29 | Bangladesh national budget totals for cost-share context | Expressing program cost as share of national budget requires the verified FY2025-26 budget document | Ministry of Finance | No - public documents; simply not yet retrieved this phase | Low

## D27 Dictionary P3
Data Dictionary for Phase 3 Files
Phase 3 research data - "NA" = not available (never zero) - compiled 2026-10-15 - derived values reference ASM-xx in D24 Assumptions
file | primary_key | contents | value_fields | units | notes
12_participation_pipeline.csv | PL-xx | Pipeline stage rows mixing verified enrollment inputs with derived cohort estimates | value | Mixed units (see unit column); NA where not applicable | All derived rows carry ASM-xx; verified rows carry SRC-xx
13_participation_scenarios.csv | scenario / metric | Scenario model: participation, placements, supervisors, sector splits for 100k/200k/300k | value | Numeric | All rows are planning assumptions (ASM-05 to ASM-09); NOT verified capacities
14_program_service_mapping.csv | discipline_cluster | Mapping of academic discipline clusters to suitable supervised service assignments | text | n/a | Example programs reference the Phase 1 program inventory (09_academic_programs.csv) and its PROG-xxxx IDs
15_sector_host_mapping.csv | sector | 14 host sectors with institutions, counts, disciplines, training, duration, capacity, equipment, confidentiality, risks, outputs | text + counts | n/a | Institution counts are the verified figures cited in source_ids column
16_capacity_model.csv | capacity_item | Theoretical hosting capacity ranges and supervisor/staffing requirements | low/medium/high | Numeric ranges | Theoretical capacity; the register explicitly separates vacancies from hosting capacity
17_financial_model.csv | cost_item | Per-participant costs (low/medium/high) and scenario totals in BDT | BDT | All monetary values in Bangladeshi Taka | Preliminary estimates; no corruption-reduction savings counted (ASM-22)
18_legal_framework.csv | legal_id | Legal instruments with verification status and relevance to the proposed program | text | n/a | Verification levels: verified official text / verified via secondary analysis / preliminary interpretation / flagged
19_international_models.csv | model_id | Six verified international comparator programs with 13 documentation fields | text | n/a | Every factual claim carries a SRC-xx reference in CSV 25
20_anticorruption_mechanisms.csv | mechanism_id (AC-xx) / safeguard_id (SG-xx) | Nine candidate mechanisms and six safeguards with problem, role, supervision, evidence, verification, referral, outcome, limitations | text | n/a | Students never exercise statutory authority; all referral routes are authorized channels
21_risk_register.csv | risk_id | Sixteen implementation risks with likelihood/impact and mitigations | text | n/a | Likelihood/impact are qualitative research judgments, not measured probabilities
22_me_framework.csv | indicator_id | Monitoring indicators by type (output/process/effectiveness/governance/impact) | text | n/a | Separates outputs from outcomes and long-term impact; allegation counts never standalone
23_phased_implementation.csv | phase_id | Five phases with durations, cohorts, scope, entry/exit criteria and decision gates | text | n/a | Each expansion is conditional on the previous gate - no automatic scaling
24_assumptions_register.csv | assumption_id | Every assumption used in Phase 3 calculations, with basis and sensitivity | text | n/a | Assumption IDs (ASM-xx) are referenced from CSVs 12, 13, 16, 17
25_source_registry_phase3.csv | source_id | 54 new sources for Phase 3 (SRC-46 to SRC-99) with URLs and access dates | text | n/a | Combined with Phase 1 registry (SRC-01 to SRC-45), the total program source base is 99 sources
26_missing_data_phase3.csv | gap_id | Twelve new data gaps (GAP-18 to GAP-29) with RTI pathways | text | n/a | Continues the Phase 1 register (GAP-01 to GAP-17); RTI drafts for high-priority gaps in Phase 1 file 10
27_data_dictionary_phase3.csv | file | This dictionary | text | n/a